## Project Plan
Avanti Press, Inc.
| ABO Proxy Replacement Project Plan |  |  |  |  | % Completed | [5 empty] | Responsibility
WBS1 | WBS2 | WBS3 | Task Description | Target Start | Actual Start | 25 | 50 | 75 | 100 | Target Finish | Actual Finish | Primary | Comments | Default Order (Hide)
1000 | Planning | [12 empty] | 1000
1001
|  | Project Planning | [11 empty] | 1002
1003
|  |  | Complete skeleton Project Plan | [10 empty] | 1004
Meet with IT Manager and review Project Plan
1018
|  | ABO Traffic Levels Review | [11 empty] | 1002
1003
|  |  | Determine average per day overall of: Hits, page views, unique visitors, bandwidth. | [9 empty] | 03/10/2015 - 06/01/2015 Hits per day: 60,761 Page Views per Day: 31,311 Visitors per day: 99 Bandwidth per day: 1.12 GB | 1004
|  |  | Determine average per day through proxy of: Hits, page views, unique visitors, bandwidth. | [9 empty] | 5/3/2015 - 5/31/2015 Hits per day: 18,230 Page Views per Day: 438 Visitors per day: 368 Bandwidth per day: 682.28 MB
|  | Consultant Evaluation | [10 empty] | Criteria: Company should be able to evaluate our current setup of using Red Hat 2 and Apache, as well as recommend a new solution based on traffic data and our requirements. Company should be aware of on premise, hosted, and cloud-based solutions. | 1002
1003
|  |  | Bischer Technologies (MI) | [9 empty] | http://www.bischer.com/ | 1004
|  |  | Dynedge (MI) | [9 empty] | http://www.dynedge.com/ | 1004
|  |  | RDX Solution (MI) | [9 empty] | http://www.rdx-solutions.com/ | 1004
|  |  | Rack911 (CA) | [9 empty] | https://www.rack911.com/ | 1004
|  |  | Samsa (MI) | [9 empty] | http://www.samsa.com/ | 1004
|  |  | CTC Technologies (MI) | [9 empty] | http://www.ctctechnologies.com/ | 1004
|  |  | Gainroot (OH) | [9 empty] | http://gainroot.co/ | 1004
|  |  | Greyhound Technologies (MI) | [9 empty] | http://www.greyhound-tech.com/ | 1004
|  |  | IDSI (MI) | [9 empty] | http://www.idsi4it.com/ | 1004
|  |  | Integrated Network Concepts (OH) | [9 empty] | http://www.integrated.net/ | 1004
|  |  | MCPc (OH) | [9 empty] | http://www.mcpc.com/ | 1004
|  |  | Suntel (MI) | [9 empty] | http://www.suntel.com/
|  |  | Server Intellect (FL) | [9 empty] | http://www.serverintellect.com
|  |  | Vision Computer Solutions (MI) | [9 empty] | http://www.vcsolutions.com
|  |  | Progent (MI) | [9 empty] | www.progent.com
1087
|  | Consultant Planning | [11 empty] | 1002
1003
Set up meeting with selected consultants
|  |  | Meet with consultants | [9 empty] | Establish scope of work | 1004
|  |  | Schedule current system evaluation | [10 empty] | 1004
|  | Consultant Current System Evaluation | [11 empty] | 1002
1003
Current System Evaluation
1004
1004
|  | Test Planning | [11 empty] | 1002
1003
Determine test users to use new IP address or subdomain
Determine test users to use new IP address or subdomain
|  | Notable Dates | [11 empty] | 1088
1089
1090
1091
1092
1093
1223
3000 | Test Implementation and Testing
Test Implementation
Create IP address / avantipress.com subdomain for testing through new proxy
Inform test users to use new method to access ABO
4000 | Production Implementation
Production Implementation
5000 | Cleanup / Close | [12 empty] | 1224
1225
1226
1227
1228