## CS6 Project Plan
Avanti Press, Inc.
| CS6 & UTS Project Plan | [5 empty] | % Completed | [5 empty] | Responsibility
|  |  |  | Target Start | Assumptions | Actual Start | 25 | 50 | 75 | 100 | Target Finish | Actual Finish | Primary | Man Hours | Comments
1000
| 1010 | Requirements
|  | 1011 | Uninstall of CS5.5 | 2012-10-15 |  | 2012-10-15 |  |  |  |  | 2012-10-22 | 2012-10-22 | EJ
|  | 1013 | Deactivation of plug-in | 2012-10-15 |  | 2012-10-15 |  |  |  |  | 2012-10-22 | 2012-10-22 | EJ
|  | 1015 | Deployment of CS6 | 2012-10-15 |  | 2012-10-15 |  |  |  |  | 2012-10-22 | 2012-10-22 | EJ
|  | 1017 | Master collection | 2012-10-15 |  | 2012-10-15 |  |  |  |  | 2012-10-22 | 2012-10-22 | EJ |  | Adam, Barry, Pete, Tom
|  | 1019 | Determine Extensis UTC client requirements | 2012-10-15 |  | 2012-10-15 |  |  |  |  | 2012-10-22 | 2012-10-22 | EJ
|  | 1021 | Determine Extensis UTC server requirements | 2012-10-15 |  | 2012-10-15 |  |  |  |  | 2012-10-22 | 2012-10-22 | EJ
|  | 1023 | Uninstall Adobe Acrobat X | 2012-10-15 |  | 2012-10-15 |  |  |  |  | 2012-10-22 | 2012-10-22 | EJ
|  | 1025 | Plug-in compatibility | 2012-10-15 |  | 2012-10-15 |  |  |  |  | 2012-10-22 | 2012-10-22 | EJ
|  | 1027 | Discuss training plans with IT Manager | 2012-11-27 |  | 11/27/2012 |  |  |  |  | 2012-11-27 | 11/27/2012 | EJ
|  | 1029 | Meet with Director of Imaging to determine optimized Photoshop settings | 2012-12-03 |  | 12/3/2012 |  |  |  |  | 2012-12-03 | 12/3/2012 | EJ/SL
|  | 1031 | Create work instruction on how to implement optimized Photoshop settings | 2012-12-03 |  | 12/3/2012 |  |  |  |  | 2012-12-07 |  | EJ |  | Lee to create document with optimized settings for retouchers vs art directors; will email to us and confer with before anything is released to employees.
1033
1035
1037
1039
1041
1043
1045
| 1110 | Testing
|  | 1111 | Validation of CS6 install | 2012-10-29 |  | 10/29/2012 |  |  |  |  | 2012-11-02 | 11/16/2012 | EJ
|  | 1113 | Feature updates and lockdown | 2012-10-30 |  | 10/29/2012 |  |  |  |  | 2012-11-02 | 11/16/2012 | EJ
|  | 1115 | Adobe Acrobat install | 2012-10-31 |  | 10/29/2012 |  |  |  |  | 2012-11-02 | 11/16/2012 | EJ
|  | 1117 | Validation of acrobat install | 2012-11-01 |  | 10/29/2012 |  |  |  |  | 2012-11-02 | 11/16/2012 | EJ
|  | 1119 | Feature updates and lockdown | 2012-11-02 |  | 10/29/2012 |  |  |  |  | 2012-11-02 | 11/16/2012 | EJ
|  | 1121 | Send email to users for info on testing | 2012-11-03 |  | 10/29/2012 |  |  |  |  | 2012-11-02 | 11/16/2012 | EJ
|  | 1123 | Identify known issues | 2012-11-04 |  | 10/29/2012 |  |  |  |  | 2012-11-02 | 11/16/2012 | EJ
|  | 1125 | Install of Extensis UTC | 2012-11-05 |  | 10/29/2012 |  |  |  |  | 2012-11-02 | 11/16/2012 | EJ
|  | 1127 | Install with deployment packages | 2012-11-06 |  | 10/29/2012 |  |  |  |  | 2012-11-02 | 11/16/2012 | EJ
|  | 1129 | Install all applicable updates | 2012-11-07 |  | 10/29/2012 |  |  |  |  | 2012-11-02 | 11/16/2012 | EJ
|  | 1131 | Create a test plan of what we what to validate | 2012-11-08 |  | 10/29/2012 |  |  |  |  | 2012-11-02 | 11/27/2012 | EJ
|  | 1133 | Review of testing plan | 2012-11-09 |  | 11/27/2012 |  |  |  |  | 2012-11-02 | 11/27/2012 | EJ/SL
|  | 1135 | Implement and complete testing plan | 2012-11-27 |  | 11/27/2012 |  |  |  |  | 2012-12-07 | 11/30/2012 | EJ
|  | 1137 | Test Photoshop CS6 optimized settings work instruction - Implement on test user systems, gather feedback by target date, make corrections | 2012-12-03 | [6 empty] | 2012-12-07 |  | EJ
1139
1141
1143
1145
| 1210 | Enterprise Deployment
|  | 1211 | Determine roll out plan | 2012-11-19 |  | 11/15/2012 |  |  |  |  | 2012-11-30 | 11/27/2012 | EJ |  | No more than a 1/3 of a department upgraded at any time
|  | 1212 | Request approval from Dave, Sheila and Lee | 2012-11-30 |  | 11/27/2012 |  |  |  |  | 2012-12-07 | 11/30/2012 | EJ |  | Awaiting response regarding if they want us to hold off until they determine training.
|  | 1213 | Communicate plan to user group | 2012-11-30 |  | 11/09/2012 |  |  |  |  | 2012-11-30 | 12/3/2012 | EJ
|  | 1214 | Contact users with plugins that will need deactivation, schedule deactivation/reactivation | 2012-11-28 |  | 11/09/2012 |  |  |  |  | 2012-11-30 | 12/3/2012 | EJ
|  | 1215 | Email Mr. Retro and let them know we will need our activation counts reset for a mass deployment on Monday | 2012-12-06 |  | 12/6/2012 |  |  |  |  | 2012-12-08 | 12/6/2012 | EJ
|  | 1216 | Perform deployment | 2012-11-19 | [6 empty] | 2012-11-30 |  | EJ
|  | 1222 | Schedule upgrades with users that can't or didn't make it on 12/10 | 2012-12-03 | [6 empty] | 2012-12-14 |  | EJ
|  | 1223 | Communicate upgrade completion | 2012-12-31 | [6 empty] | 2012-12-31 |  | EJ
|  | 1225 | Email Photoshop CS6 Optimized Settings work instruction to users | 2012-12-07 | [6 empty] | 2012-12-14 |  | EJ
|  | 1227 | Include optimized Photoshop settings as part of post deployment config | 2012-12-07 | [6 empty] | 2012-12-30 |  | EJ
1229
1231
1233
1235
1237
1239
1241
1243
1245
Training
| 1310 | 1311 | Request plans from Sheila, Dave and Lee | 2012-11-27 |  | 11/27/2012 |  |  |  |  | 2012-11-27 | 11/28/2012 | EJ |  | No plans at this time, they will set it up themselves. Got the go ahead to proceed with deployment without any mention of training.
1313
1315
1317
1319
1321
1323
1325
1327
1329
1331
1333
1335
1337
1339
1341
1343
1345