## Sheet1
Test Category | Test | Lee Land | Beth Hunwick | David Burton | Barry Borchardt | Adam Stanford | DTDE0160
CS5.5 DS Uninstall | Confirm no residual CS5.5 folders in Applications folder | Yes | Yes | Yes | N/A | N/A | Yes
CS5.5 MC Uninstall | Confirm no residual CS5.5 folders in Applications folder | N/A | N/A | N/A | Yes | Yes | N/A
CS6 DS Install | Confirm presence of CS6 software (/Applications/Adobe <ProductName> CS6/Adobe <ProductName> CS6.app) | Yes | Yes | Yes | N/A | N/A | Yes
CS6 DS Install | Confirm CS6 applications launch | Yes | Yes | Yes | N/A | N/A | Yes
CS6 DS Install | Confirm presence of Adobe Help (/Applications/Adobe/Adobe Help) | Yes | Yes | Yes | N/A | N/A | Yes
CS6 DS Install | Confirm Adobe Help launches | Yes | Yes | Yes | N/A | N/A | Yes
CS6 MC Install | Confirm presence of CS6 software (/Applications/Adobe <ProductName> CS6/Adobe <ProductName> CS6.app) | N/A | N/A | N/A | Yes | Yes | N/A
CS6 MC Install | Confirm CS6 applications launch | N/A | N/A | N/A | Yes | Yes | N/A
CS6 MC Install | Confirm presence of Adobe Help (/Applications/Adobe/Adobe Help) | N/A | N/A | N/A | Yes | Yes | N/A
CS6 MC Install | Confirm Adobe Help launches | N/A | N/A | N/A | Yes | Yes | N/A
CS6 Baseline Updates | Confirm Acrobat X ver 10.1.4 | Yes | Yes | Yes | Yes | Yes | Yes
CS6 Baseline Updates | Confirm Acrobat X FeatureLockdown | Yes | Yes | Yes | Yes | Yes | Yes
CS6 Baseline Updates | Confirm Bridge CS6 5.0.1 | Yes | Yes | Yes | Yes | Wrong ver | Yes
CS6 Baseline Updates | Confirm CSXS Infrastructure 3.0.44 | Yes | Yes | Yes | Yes | Wrong ver | Yes
CS6 Baseline Updates | Confirm Extension Manager 6.0.2 | Yes | Yes | Yes | Yes | Wrong ver | Yes
CS6 Baseline Updates | Confirm Illustrator ver 16.0.1 | Yes | Yes | Yes | Yes | Wrong ver | Yes
CS6 Baseline Updates | Confirm InDesign ver 8.0.1.406 | Yes | Yes | Yes | Yes | Wrong ver | Yes
CS6 Baseline Updates | Confirm Adobe Media Encoder 6.0.2 | Yes | Yes | Yes | Yes | Wrong ver | Yes
CS6 Baseline Updates | Confirm Adobe Photoshop CS6 13.0.1 | Yes | Yes | Yes | Yes | Yes | Yes
CS6 MC Baseline Updates | Confirm AfterEffects ver 11.0.2 | N/A | N/A | N/A | Yes | Wrong ver | N/A
Extensis Upgrade | Confirm able to launch UTC & connect | Yes | Yes | N/A | Yes | Yes | Yes
Extensis Upgrade | Confirm plugins installed for ID and IL | Yes | Yes | N/A | Yes | Yes | Yes
Extensis Upgrade | Confirm plugins run on ID and IL | Yes | Yes | N/A | Yes | Yes | Yes
Extensis Upgrade | Confirm Photoshop plugin disabled | Yes | Yes | N/A | Yes | Yes | Yes
Feedback | Spoke with user and confirmed no unknown/unresolved errors | Yes | Yes | Yes | Yes | Yes | N/A