## Preexisting
Product/Software Name | Version | Issue | Cause | Short Term Resolution | Long Term Resolution | Resolved? (Long term Resolution Implemented?)
Centrify/Mac OS X | 5.0.3 / 10.8 | Can't perform updates | OS X 10.8 Updates require 10.8 server, we do not have one | Point 10.8 updates back to Apple | Upgrade AVANTI19 to 10.8 | Yes
Centrify/Mac OS X | 5.0.3 / 10.8 | Groups shortcut is broken |  |  | Groups.inetloc shortcut not present in /Users/Shared, needs to be created | Yes
Mac OS X | 10.8 | After changing permissions in Terminal using chmod, had to perform a Get Info in order for the changes to be reflected in Finder |  |  |  | Yes
Sophos | 8 | Test machines show "Differs from Policy" in console | Due to Live Protection mode not being supported by our console version | None | Upgrade Sophos Console | Yes
Centrify | 5.0.3 | Improper Application Access settings being applied |  |  |  | Yes
Mac OS X | 10.6.8 | Users in NY cannot access folders with many items on AVANTI29 in DT via SMB | Possibly due to WAN acceleration; new Mac OS X SMB client in 10.8 may resolve this. | Do nothing; this access has not been requested and no issues have been reported in NY for some time regarding this. | Test once NY is upgraded; if still issues; schedule time to temporarily disable WAN acceleration between NY and DT on off hours to test.
Mac OS X | 10.6.8 | Permissions issues with files in users' drop boxes, and other locations. | Believe 10.8 may resolve; could also be due to users being in different primary UNIX groups | Provide support for specific files as needed | Test after Mountain Lion, test after moving everyone to same primary UNIX group
Mac OS X | 10.6.8 | Issues changing colors of folders | Believed to be due to SMB client issues in 10.6.8, Adam (who reported the issues) logged in using his own info on my Mountain Lion machine and tried to change the colors and had no issues. | None | Test after Mountain Lion. | Yes
Centrify / Mac OS X

## Non-Standard Software
Vendor | Software | Project or Post-Project | Type | Version | Deactivation required | Stated OS Compatibility | Tested OS Compatiblity | Users installed for
| Silverfast | Post-Project |  | 2.1.4 | ? |  |  | Robert Wright
| CardIRIS for Scansnap | Post-Project |  | 4.0.5 | ? |  |  | Robert Wright
| Epson Drivers | Post-Project |  |  | No |  |  | Robert Wright
| GlobeTrotter Connect Cellular Card | Post-Project |  | 1.3 |  |  |  | Chip Owen
| iPhoto Library Manager | Post-Project |  | 3.7.2 |  |  |  | Rick Ruffner
| ScanSnap | Post-Project | [5 empty] | Robert Wright
| Carbon Copy Cloner Credentials | Post-Project | [5 empty] | Robert Wright
| Readerware | Post-Project | [5 empty] | Robert Wright
| Crypt | Post-Project | [5 empty] | Rick Ruffner Laptop & Desktop
| VueScan | Post-Project | [5 empty] | Robert Wright
Alien Skin | Bokeh | Project | Photoshop Plugin | 2.0.1.481 | Yes | 10.5 and later | Yes | Barry Borchardt, Adam Stanford, Lindee Robinson, Tom Chicoine, Pete Pultz, Lee Land Desktop & Laptop
Red Giant | Knoll Light Factory for Photoshop | Project | Photoshop Plugin | 3.2 | No | 10.6 | Yes | Barry Borchardt, Adam Stanford, Lindee Robinson, Tom Chicoine, Pete Pultz, Lee Land Desktop & Laptop
Tiffen | DFXv3 | Project | Photoshop Plugin | 3.0.10.1 | Yes | 10.6 - 10.8 | Yes | Barry Borchardt, Adam Stanford, Lindee Robinson, Tom Chicoine, Pete Pultz, Lee Land Desktop & Laptop
Mister Retro | Machine Wash Deluxe | Project | Photoshop Plugin | 2.0 | Yes - must email support | 10.5 and later | Yes | Beth Hunwick, Karla Ginzinger, Megan Walsh, Adam Stanford, Barry Borchardt, Lindee Robinson, Lee Land Desktop & Laptop, Tom Chicoine, Pete Pultz
Toggl | Toggl Desktop | Project | Application | 4.94.0 | No | 10.6 and later | Yes | Barry Borchardt, Adam Stanford, Lindee Robinson
Dymo Software | Dymo Label Printer Software | Project | Application | 8.5.0 | No | 10.5 and later | Yes | Liza Pulgini, Sheila O'Hara, Helen Solomons
Xerox/EFI | Fiery Command Workstation | Project | Application | 5.4 | No | 10.6 - 10.8 | Yes | Robert Wright, Liza Pulgini
RDC Group | Accubarcode | Project | Application | 2.39 | No |  |  | Liza Pulgini, Tom Chicoine Desktop & Laptop, Pete Pultz Desktop & Laptop
Eizo | ColorNavigator | Project | Application | 6.4.2 | No | 10.4.11 - 10.8 | Yes | Tom Chicoine, Pete Pultz
OnOne | PerfectResize | Project | Photoshop Plugin | 7.0.7 | Yes | 10.6 and 10.7 | Yes | Tom Chicoine, Pete Pultz
FontGear | Font Doctor | Project | Application | 8.2.0 | No | 10.5 and later | Yes | Lori Delisi
Apago | PDF Enhancer | Project | Application | 2.6.1 | No | 10.4 and later | No - App is PowerPC; not supported on ML | Tom Chicoine
Portents | DiskTracker | Project | Application | 2.4.5 | No | 10.5 and later | Yes | Liza Pulgini, NY Hotelling Workstation, Tom Chicoine
EFI | EFI XF Client | Project | Application | 4.5.8 | No | 10.5.2 and 10.6 | Yes | Pete Pultz Laptop & Desktop, Tom Chicoine Laptop & Desktop, Karla Ginzinger, Liza Pulgini, Adam Stanford, Lindee Robinson, Robert Wright, Megan Walsh, Beth Hunwick
x-rite | MonacoPROFILER | Project | Application | 4.8.4 | No | 10.4 - 10.6 | INSTALLER FAILS | Tom Chicoine Desktop and Laptop
CHROMiX | ColorThink Pro |  | Application |  |  |  |  | Tom Chicoine Desktop and Laptop, Pete Pultz Desktop and Laptop
All installers located at \\avanti8\install\mac\mac_refresh\nonstandard
All serial numbers located in Systems Master
Installation instructions located in Systems Manual\Nonstandard Software Installation Instructions.docx

## Settings_and_Issues
Vendor | Product | Item Type (Setting / Issue) | Setting Name | Syatem-based or User-based | Setting Description | Setting Type | Location of Setting | Standard (Avanti) Setting / Resolution | Deployment Method | Where are settings contained (plist file / database file / other) | Command Line Implementation | Will need to be reapplied after updates | Status | Redeploy? | Within Project Scope?
|  | Issue | In order to use 10.8.4 we need to update GPU driver, have users test updated GPU driver for next month's updates |  |  |  |  | Test successful, will deploy next month. |  |  |  |  | Done | No | No
|  | Issue | ImageExpress crashes when connecting to projector |  |  |  |  | Added item in Mac User Training known issue |  |  |  |  | Confirmed issue with Retina. | Yes | No
|  | Issue | Files being held open by Mac OS X even after app is closed, possibly caused by quick look, thumbnail previews, | [9 empty] | Investigate
|  | Issue | Files saved from PSCS6 13.0.5 have alias bit turned on and invisible bit turned on | [9 empty] | Has not recurred, continue to monitor
|  | Issue | Permissions in ADAM folders not propagating to new files placed there | [9 empty] | Open ticket with EMC
Issue
|  | Issue | Beth can't see colors set by Barry, Lindee. I can't see colors set by Beth. |  |  |  |  | From research done, this is unreliable on network shares and is a known issue in the OS. |  |  |  |  | Done | No | No
|  | Issue | FileMaker not allowing PDF file save to Groups from design production PO |  |  |  |  | Share/server permissions issue. Works under admin account, does not work under non-admin accounts. |  |  |  |  | Investigate | No | No
|  | Issue | Xerox print driver for DTPX0524 does not allow access to Color Profile settings |  |  |  |  | Enable "Two Way Communication" |  |  |  |  | Test | Yes | No
|  | Issue | Groups mounted on desktop have the same capitalization now; can we change? |  |  |  |  | No good solution here unfortunately. |  |  |  |  | Done | Yes | No
|  | Issue | Logging on while WiFi is on and user is not on our network takes forever | [9 empty] | Investigate |  | No
|  | Issue | When not connected to Ethernet or Congress, WiFi prompt for network window keeps opening |  |  |  |  | sed -i "" 's/Prompt/DoNothing/' /Library/Preferences/SystemConfiguration/preferences.plist |  |  |  |  | Implement and Test | Yes | No
|  | Issue | Tom can't set folder icons on network shares |  |  |  |  | From research done, this is unreliable on network shares and is a known issue in the OS. |  |  |  |  | Done | No | No
|  | Issue | Bridge CS6 reporting "Insufficient disk space" |  |  |  |  | Issue with Bridge. |  |  |  |  | Resolved Marc R issue, working on Lori's | No | No
|  | Setting | Add bookmarks to Safari |  |  |  |  | Minor, to be done after all deployments complete to prevent overwriting user's bookmarks | [5 empty] | Yes | No
| Centrify | Issue | Not pulling down Kerberos ticket automatically |  |  |  |  | Minor, deferred until other issues resolved. |  |  |  |  | Investigate with Centrify | No | No
|  | Setting | Deny Time Machine and Address Book in User Group Policy for all Macs | [9 empty] | Done | No | Yes
|  | Issue | Mister Retro is not displayed in Plugins |  |  |  |  | Determined to be incorrect permissions on MWDLicense.ini file and files within MisterRetro subfolder in Plug-ins |  |  |  |  | Done | No | No
|  | Issue | Apple ID popup upon login after updating to 10.8.4 |  |  |  |  | Neither |  |  |  |  | Done | No | No
|  | Issue | Logging on while not connected to network takes forever | [9 empty] | Done | Yes | No
|  | Issue | Files being held open by Pete's machine even after he closes app |  |  |  |  | Awaiting more info from Pete |  |  |  |  | Done | No | No
|  | Issue | Permissions issues - can't rename folders, permission denied |  |  |  |  | Determined to be issues with individual folder permissions. Address as they come up. |  |  |  |  | Done | No | No
|  | Issue | Create policy specifically for NYDP0081 to allow Outlook policy |  |  |  |  | Enabled Outlook for Generic computers |  |  |  |  | Done | No | No
|  | Issue | Press check laptops - do not have access to their own user folders |  |  |  |  | Test loopback processing mode on computers |  |  |  |  | Done | No | No
|  | Issue | Beth's powerpoint jumping to other slides intermittently when she moves tablet pen |  |  |  |  | Per other users on forums; reverting to older driver resolved. Investigate. |  |  |  |  | Done | No | No
|  | Issue | Airdrop still enabled | [9 empty] | Done | Yes | No
|  | Issue | AVANTI19 running out of disk space, can't download updates |  |  |  |  | Get PO approval and move update area to Ext 1 TB HD |  |  |  |  | Get PO approval | No | No
| Mac OS X | Setting | Automatically update safe downloads |  |  |  | Security->Advanced | Off - Done by breaking Xprotect |  |  |  |  | Done | No | No
| Mac OS X | Setting | Remote Login | System | Enables/disables Remote Login | Checkbox | System Preferences -> Sharing | On | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Allow access for: | System | Allow access to all users / only specific users for remote login | Radio box / multi line text box | System Preferences -> Sharing -> Remote Login | Only these users: (wsmacadmin) |  |  |  |  | Done | No | No
| Mac OS X | Setting | Disable Apple ID / Cloud setup popup for first login 2/2 | User | Prevents apple ID / cloud setup from being displayed when a user first logs in | Config File | /System/Library/User\ Template/Non_localized/Library/Preferences/com.apple.SetupAssistant | LastSeenCloudProductVersion -string ’10.8.3′ | Script using Defaults Write | /System/Library/User\ Template/Non_localized/Library/Preferences/com.apple.SetupAssistant | sudo defaults write /System/Library/User\ Template/Non_localized/Library/Preferences/com.apple.SetupAssistant LastSeenCloudProductVersion -string ’10.8.3′ | Yes | Done | No | No
| Mac OS X | Setting | Set keyboard layout to US | [9 empty] | Done | No | No
| Mac OS X | Setting | Allow applications downloaded from <> |  |  |  | Security->General | Anywhere |  |  |  |  | Done | No | No
| Mac OS X | Setting | Privacy options (Contacts, Location Services, Anonymous Statistics) |  |  |  | Security->Privacy | All Off |  |  |  |  | Done | No | No
| Mac OS X | Setting | Computer sleep (AC Power) |  |  |  | Energy Saver | Never | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Hard drive sleep (AC Power) |  |  |  |  | Off | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Screen saver idle time |  |  |  |  | 60 minutes | User Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Disable iCloud control panel |  |  |  | Centrify | [5 empty] | Done | No | No
| Mac OS X | Setting | Set NetBIOS name to computer name | [9 empty] | Done | No | No
| Mac OS X | Setting | wsmacadmin -> create account, administrator | [9 empty] | Done | No | No
| Mac OS X | Setting | Display login window as |  |  |  |  | Name and Password | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Show fast user switch menu |  |  |  |  | On | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Automatically check for updates |  |  |  |  | Off | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Disable location services | [9 empty] | Done | No | No
| CUPC | Setting | Username: Username (if possible) | [9 empty] | Deferred | No | No
| Mac OS X | Setting | Prevent association of user account with Apple ID | [9 empty] | Deferred | No | No
| Mac OS X | Setting | wsmacadmin -> Allow user to reset password with apple ID |  |  |  |  | Permanently Disable if possible |  |  |  |  | Deferred | No | No
| Mac OS X | Issue | wsmacadmin account has allow unsigned applications turned off | [9 empty] | Deferred | No | No
| Centrify | Issue | Centrify -- When using 802.1x profile and directory authentication is enabled within the profile; user is unable to connect to Congress | [9 empty] | Deferred | No | No
| Centrify | Issue | Non-expire accounts displaying password expired message | [9 empty] | Deferred | No | No
|  | Issue | When sorted by Kind, folder headings will also appears as individual folders, and window does not respond to selection if you are out of the window. | [9 empty] | Deferred | No | No
|  | Issue | Beth receiving message "Could not activate Font due to OS activation issue" |  |  |  |  | Open ticket with Extensis |  |  |  |  | Deferred - Known Issues - intermittent font activation errors in Mac OS X 10.8.3 | No | No
|  | Setting | Disable automatic updates for NVIDIA Driver Manager | [9 empty] | Deferred - Post config | No | No
|  | Setting | Disable Show NVIDIA Driver Manager in menu bar | [9 empty] | Deferred - Post config | No | No
|  | Issue | Pete's machine did not pull down Kerberos ticket; keep an eye on this | [9 empty] | Done | No | No
Centrify | DirectControl | Setting | Domain Controller mode |  |  |  |  | Automatic |  |  |  |  | Done | No | No
| Mac OS X | Setting | Remote Management | System | Enables/disables Remote Management | Checkbox | System Preferences -> Sharing | On | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | VNC viewers may control screen with password: | System | Allows VNC viewers to control computer | Checkbox / text box | System Preferences -> Sharing -> Remote Management -> Computer Settings | On (VNC password) |  |  |  |  | Done | No | No
| Mac OS X | Setting | Disable Apple ID / Cloud setup popup for first login 1/2 | User | Prevents apple ID / cloud setup from being displayed when a user first logs in | Config File | /System/Library/User\ Template/Non_localized/Library/Preferences/com.apple.SetupAssistant | DidSeeCloudSetup -bool TRUE | Script using Defaults Write | /System/Library/User\ Template/Non_localized/Library/Preferences/com.apple.SetupAssistant | sudo defaults write /System/Library/User\ Template/Non_localized/Library/Preferences/com.apple.SetupAssistant DidSeeCloudSetup -bool TRUE | Yes | Done | No | No
| Mac OS X | Setting | Set country to US | [9 empty] | Done | No | No
| Mac OS X | Setting | Disable automatic login |  |  |  | Security->General | On | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Firewall state |  |  |  | Security->Firewall | Off | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Require an administrator password to access locked preferences |  |  |  | Security->Advanced | On | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Display sleep (AC Power) |  |  |  | Energy Saver | 70 minutes | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Disable Mail, Contacts and Calendars control panel |  |  |  | Centrify | [5 empty] | Done | No | No
| Mac OS X | Setting | Set computer name to provided name | [9 empty] | Done | No | No
| Mac OS X | Setting | Set sharing name to computer name |  |  |  |  | <Computer Name> |  |  |  |  | Done | No | No
| Mac OS X | Setting | wsmacadmin -> allow user to administer |  |  |  |  | On |  |  |  |  | Done | No | No
| Mac OS X | Setting | Guest account |  |  |  |  | Disable |  |  |  |  | Done | No | No
| Mac OS X | Setting | Show password hints |  |  |  |  | Off | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Automatically download purchased Apps |  |  |  |  | Off |  |  |  |  | Done | No | No
Absolute | Absolute Manage Agent | Setting | SD Server address |  |  |  |  | avanti13 |  |  |  |  | Done | No | No
Absolute | Absolute Manage Agent | Setting | SD Server package check interval |  |  |  |  | 15 min |  |  |  |  | Done | No | No
Absolute | Absolute Manage Agent | Setting | SD Server certificate |  |  |  |  | <avanti13 cert> |  |  |  |  | Done | No | No
Absolute | Absolute Manage Agent | Setting | LM Server address |  |  |  |  | avanti13 |  |  |  |  | Done | No | No
Absolute | Absolute Manage Agent | Setting | LM Server certificate |  |  |  |  | <avanti13 cert> |  |  |  |  | Done | No | No
Absolute | Absolute Manage Agent | Setting | Server address |  |  |  |  | avanti13 |  |  |  |  | Done | No | No
Absolute | Absolute Manage Agent | Setting | Server certificate |  |  |  |  | <avanti13 cert> |  |  |  |  | Done | No | No
Centrify | DirectControl | Setting | Computer join name |  |  |  |  | <computer name> |  |  |  |  | Done | No | No
Centrify | DirectControl | Setting | Domain |  |  |  |  | avantipress.com |  |  |  |  | Done | No | No
Centrify | DirectControl | Setting | Zone |  |  |  |  | Avanti |  |  |  |  | Done | No | No
Centrify | DirectControl | Setting | Container |  |  |  |  | Computers |  |  |  |  | Done | No | No
| Word, Outlook, Excel, Powerpoint | Setting | Turn off welcome screen | [9 empty] | Done | No | No
| Word, Excel, Powerpoint | Setting | Set autorecover time |  |  |  |  | 3 minutes |  |  |  |  | Done | No | No
| FileZilla | Setting | Run once dialog deactivated | [9 empty] | Done | No | No
| FileZilla | Setting | Update check |  |  |  |  | Off |  |  |  |  | Done | No | No
| FileZilla | Setting | FTP mode setting |  |  |  |  | Active |  |  |  |  | Done | No | No
| FileZilla | Setting | Show site manager on startup |  |  |  |  | On |  |  |  |  | Done | No | No
| iTerm | Setting | Connect to sweetpea on startup |  |  |  |  | On |  |  |  |  | Done | No | No
| iTerm | Setting | Scrollback lines |  |  |  |  | 10000 |  |  |  |  | Done | No | No
| iTerm | Setting | Character encoding |  |  |  |  | Latin-US (DOS) |  |  |  |  | Done | No | No
| iTerm | Setting | Report Terminal Type |  |  |  |  | vt220 |  |  |  |  | Done | No | No
| iTerm | Setting | Enable xTerm mouse reporting |  |  |  |  | Off |  |  |  |  | Done | No | No
| iTerm | Setting | Load Preset "xterm with Numeric Keypad" | [9 empty] | Done | No | No
| iTerm | Setting | Set F5 to ^[[25~ | [9 empty] | Done | No | No
| iTerm | Setting | Delete key sends ^H | [9 empty] | Done | No | No
| UTC | Setting | Deploy server info via com.extensis.UniversalTypeClient.conf | [9 empty] | Done | No | No
| AnyConnect VPN | Setting | Set VPN Group |  |  |  |  | SSLVPNClient |  |  |  |  | Done | No | No
| AnyConnect VPN | Setting | Set vpn server |  |  |  |  | vpn.avantipress.com |  |  |  |  | Done | No | No
| Mac OS X | Setting | Disable setup assistant | [9 empty] | Done | No | No
| AD | Manual Config Step | Once done, enable "user must change password on next logon" | [9 empty] | Done | No | No
| Mac OS X | Manual Config Step | Add user's user folder to dock (smb://avanti16/users/userfolders/username or smb://avantiny3/users/userfolders/username) | [9 empty] | Done | No | No
| Mac OS X | Setting | Set Time Zone to Detroit or NY |  |  |  |  | Detroit |  |  |  |  | Done | No | No
| Mac OS X | Setting | Allow access for: | System | Allow access to all users / only specific users for remote lManagement | Radio box / multi line text box | System Preferences -> Sharing -> Remote Management | Only these users: (wsmacadmin) |  |  |  |  | Done | No | No
| Mac OS X | Setting | Show Remote Management status in menu bar | System | Shows remote management status in menu bar | Checkbox | System Preferences -> Sharing -> Remote Management -> Computer Settings | On |  |  |  |  | Done | No | No
| Mac OS X | Setting | Remote Management options | System |  |  | System Preferences -> Sharing -> Remote Management -> Options | All On |  |  |  |  | Done | No | No
| Mac OS X | Setting | Require password < > after sleep or screen saver begins |  |  |  | Security->General | Immediately |  |  |  |  | Done | No | No
| Mac OS X | Setting | Configure WiFi for Congress (802.1x, login, password, etc) | [9 empty] | Done | No | No
Apple | Mac OS X | Setting | New Finder Windows Show: |  |  |  |  | Add user's home |  |  |  |  | Done | No | No
Apple | Finder | Setting | Sidebar |  |  |  |  | Set Home to ON |  |  |  |  | Done | No | No
Apple | Keychain Access | Setting | Show keychain status in menu bar |  |  |  |  | On |  |  |  |  | Done | No | No
| Word, Outlook, Excel, Powerpoint | Setting | Feedback |  |  |  |  | OFF |  |  |  |  | Done | No | No
| CUPC | Setting | License accepted -- com.Cisco.CiscoUPC.plist present in ~/Library/Preferences w/ version info | [9 empty] | Done | No | No
| CUPC | Setting | Login server: AVANTI24 | [9 empty] | Done | No | No
| i1 Profiler | Setting | Tray - Deactivate re-profile reminder | [9 empty] | Done | No | No
| i1 Profiler | Setting | Application - Check version and license status at startup |  |  |  |  | Off |  |  |  |  | Done | No | No
| i1 Profiler | Setting | Check for updates |  |  |  |  | Off |  |  |  |  | Done | No | No
| Mac OS X | Setting | Restrict access to app Game Center | [9 empty] | Done | No | No
| Mac OS X | Setting | Disable air drop | [9 empty] | Done | No | No
| Illustrator | Issue | Can't launch; tries to launch Software Update and fails |  |  |  |  | URL pointing to wrong place |  |  |  |  | Done | No | No
| Mac OS X | Setting | Remove Time Machine from menu bar | [9 empty] | Done | No | No
| Mac OS X | Setting | Deploy shortcuts to Groups shares to /Users/Shared | [9 empty] | Done | Yes | No
| Mac OS X | Setting | Add Groups shortcuts to docks | [9 empty] | Done | No | No
| Mac OS X | Setting | Login wsmacadmin automatically after DeployStudio process for CS6 install | [9 empty] | Done | No | No
| Mac OS X | Setting | Scroll direction natural |  |  |  | Mouse | Off |  |  |  |  | Done | No | No
| Mac OS X | Issue | 802.1x profile not connecting to Congress - Workaround -- turned off directory authentication; user must enter username/password upon first connect. | [9 empty] | Done | No | No
| Mac OS X | Setting | Computer sleep (Battery) |  |  |  | Energy Saver | 90 minutes | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Display sleep (Battery) |  |  |  | Energy Saver | 70 minutes | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Hard drive sleep (Battery) |  |  |  |  | Off | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Require admin authentication to create computer to computer networks | [9 empty] | Done | No | No
Apple | Safari | Setting | Homepage |  |  |  |  | intranet.avantipress.com |  |  |  |  | Done | No | No
| Mac OS X | Setting | All CDs and DVDs options |  |  |  | CDs and DVDs | Ignore |  |  |  |  | Done | No | No
| Mac OS X | Setting | Time Server |  |  |  |  | Set based on connected DC |  |  |  |  | Done | No | No
| CS6 | Issue | CS6 DS install failure |  |  |  |  | Caused by Safari being open when run |  |  |  |  | Done | No | No
| Outlook | Setting | Add Exchange account | [9 empty] | Done | No | No
| Outlook | Setting | Authentication method: Username and password | [9 empty] | Done | No | No
| Outlook | Setting | Enter signature into Standard signature | [9 empty] | Done | No | No
| Outlook | Setting | Assign Standard signature to AvantiPress account | [9 empty] | Done | No | No
| Outlook | Setting | Hide on my computer |  |  |  |  | On |  |  |  |  | Done | No | No
| Outlook | Setting | Make Outlook default email app |  |  |  |  | On |  |  |  |  | Done | No | No
| Outlook | Setting | Check addresses of recipients |  |  |  |  | On |  |  |  |  | Done | No | No
| Outlook | Setting | Time zone set to Eastern time | [9 empty] | Done | No | No
| Mac OS X | Setting | Associate WAV files with Quicktime (not iTunes) | [9 empty] | Done | No | No
Apple | Safari | Setting | Show develop menu in menu bar |  |  |  |  | On |  |  |  |  | Done | No | No
| Acrobat | Setting | Turn off prompt for default PDF app | [9 empty] | Done | No | No
| Mac OS X | Setting | Dock icons |  |  |  |  | Acrobat, Bridge, Illustrator, InDesign, Photoshop, CUPC, FileMaker, FileZilla, Word, Excel, Powerpoint, Outlook, Safari, UTC, iTerm, ImageExpress (laptop only), AnyConnect (laptop only) |  |  |  |  | Done | No | No
| Mac OS X | Issue | Upon first login, sync conflicts for .localized files | [9 empty] | Done | No | No
| Photoshop CS6 | Setting | Set scratch disk to "SCRATCH" volume | [9 empty] | Done | No | No
| Word, Outlook, Excel, Powerpoint | Setting | User information (First, Last, Company, Email) | [9 empty] | Done | No | No
| Acrobat | Issue | Updater coming up | [9 empty] | Done | No | No
| Mac OS X | Issue | Syncing extraneous folders: Microsoft User Data, Containers, Calendars, Gamekit | [9 empty] | Done | No | No
| Group Policy | Setting | Create GPs for Systems | [9 empty] | Done | No | No
| Flash | Issue | Disable flash updates script failing | [9 empty] | Done | No | No
| Mac OS X | Setting | Specify software update server |  |  |  |  | On: avanti19 | Computer Group Policy |  |  |  | Done | No | No
| Mac OS X | Setting | Remove App Store, Reminders, Notes from users' dock | [9 empty] | Done | No | No
| Mac OS X | Setting | Add shortcut to FM launcher in NY GP | [9 empty] | Done | No | No
| ImageExpress | Issue | Prompts for admin credentials upon first login | [9 empty] | Done | No | No
| iTerm | Issue | Lines wrapping randomly - Change 'report terminal' to xterm | [9 empty] | Done | No | No
| Mac OS X | Issue | Cannot connect to App Store, but can view softwareupdate -l |  |  |  |  | Need to unblock Ax.init.itunes.apple.com in Websense |  |  |  |  | Done | No | No
|  | Issue | Pete cannot access his color profiles in the 'Assign Profile' item in Photoshop CS6 |  |  |  |  | Needed to convert profiles to CMYK |  |  |  |  | Done | No | No
|  | Setting | Set App Store to update only mode | [9 empty] | Done | No | No
| Centrify / EMC | Issue | Sync permissions errors when syncing from non-admin account, sync still appears to work |  |  |  |  | Fixed share level permissions |  |  |  |  | Done | No | No
| Group Policy | Setting | Create GPs for DT Desktops, and NY Desktops and Laptops |  |  |  |  | Created |  |  |  |  | Done | No | No
|  | Issue | Pete has noticed that folders/files are duplicating post-sync |  |  |  |  | Asked Pete to stop manually syncing intermittently |  |  |  |  | Done | No | No
Absolute | Absolute Manage Admin | Setting | Include in patch management |  |  |  |  | On |  |  |  |  | Done - Manual |  | No
Absolute | Absolute Manage Admin | Setting | Only use Absolute Manage for OS Updates |  |  |  |  | On |  |  |  |  | Done - Manual |  | No
| Outlook | Setting | Change Empty Deleted items schedule to On Quit | [9 empty] | Done - Manual |  | No
| Outlook | Setting | Change Empty Deleted items schedule to point to user's Exchange deleted items folder | [9 empty] | Done - Manual |  | No
| Outlook | Setting | Add users' public folders to favorites, subscribe | [9 empty] | Done - Manual |  | No
| Mac OS X | Issue | Confirm user with preexisting snow leopard data will not overwrite default user template settings | [9 empty] | Done - no issues |  | No
Apple | Keychain Access | Setting | Search directory services for certificates |  |  |  |  | On |  |  |  |  | Done - Not necessary |  | No
| ImageExpress | Setting | Network path set to Ethernet 1 if possible | [9 empty] | Done - Not possible, as this changes |  | No
| ImageExpress | Setting | Error message on startup acknowledged | [9 empty] | Done - This message is unavoidable |  | No
| Mac OS X / Quadro 4000 | Issue | Rotating secondary display via System Prefs-> Display causes crash: Lee Land |  |  |  |  | Updated GPU drivers resolved |  |  |  |  | Done | No | No
|  | Setting | Pete has requested we move all users' color profiles into 'manual' folders inside their original location, to prevent them from being automatically loaded. Locations are /Library/Application Support/Adobe/Color/Profiles (*.icc) and Settings (*.csf) and /Library/ColorSync/Profiles/*.icc |  |  |  |  | Scripted this; included it in deployment |  |  |  |  | Done | No | No
|  | Setting | Disable Java update check |  |  |  |  | Scripted this; included it in deployment |  |  |  |  | Done | No | No
|  | Issue | Websense Auth doesn't work |  |  |  |  | Added to AM packages |  |  |  |  | Done | No | No
|  | Issue | Can't acces CUPC over VPN |  |  |  |  | Tested on 192.168.0 and 192.168.2 source subnets; these are incompatible with our VPN / VOIP settings. Retested on 4G WiFi card, no issues. |  |  |  |  | Done | No | No
|  | Issue | Illustrator requires Java 6 |  |  |  |  | Readded Java 6 deployment |  |  |  |  | Done | No | No
|  | Setting | Add UTC, AfterEffects, Cisco VPN, ImageExpress |  |  |  |  | Added |  |  |  |  | Done | No | No
|  | Issue | Modify docksetup item to appear before userfolders item |  |  |  |  | Rearranged items in Mac Deployment Guide |  |  |  |  | Done | No | No
|  | Issue | Add item immediately before 'perform manual sync' to click cancel on the deleted items prompt |  |  |  |  | Added item to Mac Deployment Guide |  |  |  |  | Done | No | No
|  | Issue | Add item to determine user's current computer name in provisioning guide |  |  |  |  | Added item to Mac Provisioning Guide |  |  |  |  | Done | No | No
|  | Issue | Photoshop message "Could not synchronize color profiles" |  |  |  |  | Added item to Mac Deployment Guide |  |  |  |  | Done | No | No
|  | Issue | When updating user's password, they will be prompted by Outlook to reenter their new password, make sure they know this. |  |  |  |  | Added item to Mac Deployment Guide |  |  |  |  | Done | No | No
|  | Issue | Add to procedure to check for Websense auth upon login (Launch Safari, browse to www.bbc.co.uk) and authenticate if prompted as domain admin |  |  |  |  | Added item to Mac Training |  |  |  |  | Done | No | No
|  | Issue | To give Pete access to New Release PDFs, needed to create symbolic link to folder in Volumes and place it in his Downloads folder |  |  |  |  | Placed procedure in Mac Deployment Procedure |  |  |  |  | Done | No | No
|  | Issue | "Recommended" color profiles present in /Library |  |  |  |  | Updated script |  |  |  |  | Done | Yes | No
|  | Issue | Deactivated Update-only mode for App store for Lee Land's computer |  |  |  |  | sudo defaults write /Library/Preferences/com.apple.appstore restrict-store-softwareupdate-only -bool no |  |  |  |  | Done | No | No
|  | Issue | OnOne Perfect Resize did not deactivate properly |  |  |  |  | S/N in Systems Master incorrect, reentered both S/Ns |  |  |  |  | Done | No | No
|  | Issue | Media profiles |  |  |  |  | Added item to Nonstandard Software Guide |  |  |  |  | Done | No | No
|  | Issue | Library/Avanti/Scripts folder closes after restart |  |  |  |  | Added item to Mac Deployment procedure |  |  |  |  | Done | No | No
|  | Issue | Press check laptops - How to disable SSO or sync only on Desktop machines? |  |  |  |  | Use loopback group policy prcessing |  |  |  |  | Done | No | No
|  | Issue | OnOne Perfect Resize will not activate |  |  |  |  | Activation count needs to be reset; install updated version |  |  |  |  | Done | No | No
|  | Issue | Incorrect permissions on User_Folders.sh script |  |  |  |  | Added execute bit to User_Folders |  |  |  |  | Done | Yes | No
|  | Issue | Change User_Folders.sh script to be double clickable |  |  |  |  | Changed extension to .command |  |  |  |  | Done | Yes | No
|  | Issue | Password protect netboot image |  |  |  |  | Recreated NetBoot image with password |  |  |  |  | Done | No | No
|  | Issue | Copy of Nonstandard software takes a long time |  |  |  |  | Zipped up files in Nonstandard, placed in Nonstandard_Zipped.zip |  |  |  |  | Done | No | No
|  | Issue | When some of Karla's older files transferred, they came across as UNIX files |  |  |  |  | No other users have experienced these issues |  |  |  |  | Done | No | No
|  | Issue | Base image didn't deploy properly on Meg's machine |  |  |  |  | Preexisting hard drive with name "Macintosh HD" caused issues, add item to Mac Deployment Procedure to rename hard drive to anything but "Macintosh HD" if using a non-new hard drive. |  |  |  |  | Done | No | No
|  | Issue | Can't send email to users in local contact groups |  |  |  |  | Update to Office 14.3.4 |  |  |  |  | Done | No | No
|  | Issue | Lee/Aubrey -- Brush disappears in Photoshop when performing magnifications, pen sticks to layers and moves them around when hovering over them, pen arbitrarily changes brush sizes, tools stick |  |  |  |  | Adobe reports this is a known bug with Mac OS X 10.8 |  |  |  |  | Done - Known issue | No | No
|  | Setting | Turn on scroll bars always |  |  |  |  | defaults write NSGlobalDomain AppleShowScrollBars -string "Always" |  |  |  |  | Execute as script on current users computers | Yes | No
|  | Setting | Add DTPZ0529 to printer deployment package

## Accounts Deployed
wsmacadmin
Full Name | wsmacadmin
Account Name | wsmacadmin
Password | <password>
Allow my apple ID to reset this user's password (DISABLED)
Require password when logging in (ENABLED)
No password hint