## Sheet1
| Group 1 (Detroit) | [5 empty] | Group 2 (Detroit) |  |  | Group 3 (Detroit) |  |  |  | Group 4 (NY)
Task | Lee Land Desktop | Lee Land Laptop | Tom Chicoine Desktop | Pete Pultz Desktop | Beth Hunwick | Karla Ginzinger | Megan Walsh | Barry Borchardt | Adam Stanford | Lindee Robinson | Sheila O'Hara | Liza Pulgini | Lori Delisi | Helen Solomons | David Burton | David Laubach | Aubrey Stalnaker | Marc Rampulla
Scheduling
Deployment and training scheduled with user or user will need manual scheduling (mark M).
Information
User informed that Systems will configure Outlook, but once logged in they will need to allow items to download from the server. The less in their mailbox, the less time this will take.
User informed that any items they wish to keep on their machine MUST be copied to ~/Documents, ~/Pictures (iPhoto Library). Color Profiles in ~/Library/Colorsync will be copied; as well as Safari favorites. Anything NOT in one of these folders will be NOT be kept.
User advised to clean up ~/Documents and ~/Pictures. If there is too much data here, the migration may overflow into the following day.
User informed that preferences will not be transferred during this process and things will need to be reconfigured.
Group 1 user instructed to shut down and perform final sync on Friday when they leave
Group 1 user instructed to contact Systems Monday following their upgrade for assistance logging in
Group 1 user informed that email will be unavailable Saturday through Monday until password reset
Group 2/3/4 user informed that Systems will perform configuration first, and allow the user's initial sync to run at logout, and that this sync will need to be validated before they can log in.
Group 2/3/4 user informed that they must leave and start their final sync by 5 PM on Monday, or the length of time the upgrade process takes for their machine will be extended and their machine may not be ready Tuesday morning when they arrive.
Group 2/3/4 user informed that if the user’s machine setup extends past 7 PM, the remainder will be completed Tuesday.
Group 2/3/4 user instructed to shut down and perform final sync on Monday when they leave
Group 2/3/4 user instructed to contact Systems Tuesday following their upgrade for assistance logging in
Group 2/3/4 user informed that email will be unavailable Monday night through Tuesday until password reset
Preparation
Non-standard apps checked on user's machine with Absolute Manage
Validated non-standard apps with user and confirmed that there were no other non-standard apps needing installation
Determined non-standard software with license activation schemes
Let the user know the status of their non-standard apps; whether they are incompatible or will be reinstalled
Final release configuration applied to user's replacement machine (if applicable)
Group 4 user's machine and accessories shipped to NY
Group 4 user's machine and accessories confirmed received by NY
Training
User attended Systems training on Mac OS X 10.8, Office 2011 (list date) | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-06-10 | 2013-06-10 | 2013-06-10 | 2013-06-17 | 2013-06-17 | 2013-06-17 | 2013-06-17 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08
Deployment
Logged into wsmacadmin account on each reused machine or machine pending replacement and deactivated non-standard software with license activation schemes
User's Final Sync status validated -- .FileSyncHistory file checked and passed; or failed and was resolved.
Group 1 user's Initial Sync performed, and status validated -- .FileSyncHistory file checked and passed; or failed and was resolved.
User's AD User and Computer objects moved to correct location
AD Password reset performed on user's AD account
Hardware upgraded on reused machines / Replaced machines pending replacement with new hardware and accessories
Base image deployed to reused machines
Post config deployed to machine
Non-standard software installed
Non-standard software activated (if using license activation scheme)
Group 2/3/4 user's system logged out, allowing Initial Sync to start
Turnover to User
Group 2/3/4 Initial Sync status validated -- .FileSyncHistory file checked and passed; or failed and was resolved.
Walked user through password reset; password reset completed and keychain updated. Advised user they will need to reenter their password in Outlook and click remember password.
Users instructed to contact the HelpDesk with any further issues or questions
Websense and Universal Type Server resynced with Active Directory
User's AD account set to change password at next login