## Project Plan
Avanti Press, Inc.
| Mac Refresh Project Plan |  |  |  |  | % Completed | [5 empty] | Responsibility
WBS1 | WBS2 | WBS3 | Task Description | Target Start | Actual Start | 25 | 50 | 75 | 100 | Target Finish | Actual Finish | Primary | Man Hours | Comments | Default Order (Hide)
1000 | Planning |  |  | 2013-02-11 | 2/11/13 |  |  |  |  | 2013-05-20 | 2013-06-27 | EJ |  |  | 1000
1001
| 1100 | Project Planning |  | 2013-02-11 | 2013-02-11 |  |  |  |  | 2013-04-12 | 2013-04-11 | EJ |  |  | 1002
1003
|  | 1101 | Complete Project Plan | 2013-02-11 | 2/11/2013 |  |  |  |  | 2013-02-19 | 2013-02-20 | EJ |  |  | 1004
|  | 1102 | Review Project Plan with IT Manager | 2013-02-20 | 2013-02-20 |  |  |  |  | 2013-02-20 | 2013-02-20 | EJ/SL |  |  | 1005
|  | 1103 | Review updated Project Plan with Systems team | 2013-02-21 | 2013-02-21 |  |  |  |  | 2013-03-04 | 2013-03-08 | EJ/SYS |  |  | 1006
|  | 1104 | Revise Project Plan based on discussion with Systems team | 2013-03-05 | 2013-03-08 |  |  |  |  | 2013-03-08 | 2013-03-08 | EJ |  |  | 1007
|  | 1105 | Provide project plan and deployment checklist to department heads of Creative, Design and Production. Establish recurring project plan update frequency. | 2013-03-08 | 2013-03-08 |  |  |  |  | 2013-03-08 | 2013-03-08 | EJ |  | Biweekly update frequency; starting on 3/8/2013. | 1008
|  | 1106 | Once Project Plan approved by IT Manager, create and provide Mac Pros with document that clearly defines where we will need their help to enable them to provide accurate Scope of Work; and provide updated Application List and desired scheduling. | 2013-03-05 | 2013-03-05 |  |  |  |  | 2013-03-08 | 2013-03-07 | EJ |  | Should include set up of image deployment server, development of base image for Desktop and Laptop, generation of deployment packages for standard applications and their settings, revision of images/packages after test by Systems, revision of images/packages after test by users, some support on image deployment servers / images / packages post-deployment, and the creation of processes and documentation for: - Image creation, image updates, app deployment package creation, app settings package creation, image deployment. | 1009
|  | 1107 | Once Project Plan approved by IT Manager, speak to Mac Professionals regarding scheduling | 2013-03-06 | 2013-03-06 |  |  |  |  | 2013-03-08 | 2013-03-07 | EJ/MP |  |  | 1010
|  | 1108 | Once Mac Professionals has confirmed scheduling availability, speak with Department heads, see if there is any issue with tentative deployment dates | 2013-03-11 | 2013-04-01 |  |  |  |  | 2013-03-11 | 2013-04-01 | EJ |  | We will need to approve the project quote first before they can confirm availability. Email sent with tentative dates. | 1011
|  | 1109 | Request quote and scope of work documentation from Mac Professionals | 2013-03-12 | 2013-03-12 |  |  |  |  | 2013-03-12 | 2013-03-12 | EJ/MP |  |  | 1012
|  | 1110 | Review quote and scope of work with IT Manager | 2013-03-13 | 2013-03-13 |  |  |  |  | 2013-03-13 | 2013-03-15 | EJ/SL |  |  | 1013
|  | 1111 | Cut PO and approve quote with Mac Professionals | 2013-03-14 | 2013-03-14 |  |  |  |  | 2013-03-14 | 2013-03-26 | EJ/MP |  | Will need to speak with Apple's business team before cutting PO / approving quote. | 1014
|  | 1112 | Schedule image development with Mac Pros | 2013-03-15 | 2013-03-15 |  |  |  |  | 2013-03-15 | 2013-04-01 | EJ/MP |  | Will need to confirm availability with department heads first before scheduling image deployment. | 1015
|  | 1113 | Divide users into 4 groups | 2013-03-18 | 2013-03-06 |  |  |  |  | 2013-03-18 | 2013-03-06 | EJ |  | Group 1: Lee Land Laptop, Lee Land Desktop, Beth Hunwick, Karla Ginzinger, Pete Pultz, Tom Chicoine. Group 2: Meg Walsh, Liza Pulgini, Adam Stanford, Barry Borchardt, Betsy Cox Group 3: Lindee Robinson, Sheila O’Hara, Lori Delisi, Tom Chicoine (Press Check Laptop), Pete Pultz (Press Check Laptop) Group 4: Helen Solomons, David Burton, David Laubach, Aubrey Stalnaker, Marc Rampulla | 1016
|  | 1114 | Determine expanded test users, 1-2 users from each dept -- Discuss with IT Manager | 2013-04-01 | 2013-04-01 |  |  |  |  | 2013-04-01 | 2013-04-01 | EJ |  | Creative: Aubrey Stalnaker, Lee Land Production: Pete Pultz Design: Beth Hunwick
|  | 1115 | Speak to test users and confirm availability | 2013-04-01 | 2013-04-01 |  |  |  |  | 2013-04-12 | 2013-04-11 | EJ |  | Confirmed availability with Aubrey, Pete and Beth and their managers.
|  | 1116 | Confirm availability of test users with department head (if applicable) | 2013-04-10 | 2013-04-10 |  |  |  |  | 2013-04-12 | 2013-04-11 | EJ |  | Confirmed availability with Aubrey, Pete and Beth and their managers.
|  | 1117 | Schedule testing with 1-2 users and the department head from each department of Creative, Design and Production | 2013-03-19 | 2013-03-19 |  |  |  |  | 2013-03-19 | 2013-04-11 | EJ |  | Lee Land is interested in testing. Adam Stanford and Beth Hunwick also tested last time and were ideal test candidates. It is extremely important we get someone from Production, as they use custom software that needs to be tested with the image. It would be wise to test with an NY user also, by prepping the machine in Detroit and shipping it to NY. | 1017
1018
| 1200 | Software Licensing |  | 2013-02-19 | 2013-02-19 |  |  |  |  | 2013-04-03 | 2013-04-01 | EJ |  |  | 1019
1020
|  | 1201 | Determine # of Mac OS X Mountain Lion Upgrades Needed | 2013-03-11 | 2013-03-11 |  |  |  |  | 2013-03-21 | 2013-03-12 | EJ |  | We will need 14 licenses for our workstations, 1 for AVANTI19. Minimum # of licenses required for volume licensing is 20. | 1021
|  | 1202 | Determine # of Microsoft Office 2011 licenses needed | 2013-02-25 | 2013-02-25 |  |  |  |  | 2013-03-08 | 2013-03-12 | EJ |  | We will need 26 licenses. | 1022
|  | 1203 | Determine # of Centrify DirectControl Licenses Needed | 2013-02-19 | 2013-02-19 |  |  |  |  | 2013-02-19 | 2013-02-19 | EJ |  | No licenses needed | 1023
|  | 1204 | Determine # of Adobe CS DS/MC licenses needed | 2013-02-19 | 2013-02-19 |  |  |  |  | 2013-02-19 | 2013-02-19 | EJ |  | No licenses needed | 1024
|  | 1205 | Determine # of FileMaker Pro 11 licenses needed | 2013-02-19 | 2013-02-19 |  |  |  |  | 2013-02-19 | 2013-02-19 | EJ |  | No licenses needed | 1025
|  | 1206 | Determine # of Sophos Anti-Virus licenses needed | 2013-02-25 | 2013-03-05 |  |  |  |  | 2013-03-08 | 2013-03-05 | EJ |  | We require 151 licenses total. As we will be renewing in the near future, we will true up then. | 1026
|  | 1207 | Determine # of Extensis UTS client access licenses needed | 2013-02-19 | 2013-02-19 |  |  |  |  | 2013-02-19 | 2013-02-19 | EJ |  | No licenses needed | 1027
|  | 1208 | Determine # of Absolute Manage clients | 2013-02-25 | 2013-03-05 |  |  |  |  | 2013-03-08 | 2013-03-05 | EJ |  | We require 145 licenses total. | 1028
|  | 1209 | Determine if we need to purchase any additional licenses for Presence/CUPC/Jabber | 2013-02-25 | 2013-02-25 |  |  |  |  | 2013-03-08 | 2013-02-28 | EJ |  | We will continue to use version 7.1.2 as there have been no major issues determined our testing; thus no additional licenses are necessary. | 1029
|  | 1210 | Confirm license procurement complete | 2013-03-22 | 2013-03-05 |  |  |  |  | 2013-04-03 | 2013-04-01 | EJ |  | All licenses procured. | 1030
1031
| 1300 | Software Prerequisites |  | 2013-02-19 | 2013-02-19 |  |  |  |  | 2013-03-29 | 2013-06-27 | EJ |  |  | 1032
1033
|  | 1301 | Determine FTP Client | 2013-02-19 | 2013-02-19 |  |  |  |  | 2013-02-19 | 2013-02-19 | EJ |  | FileZilla | 1034
|  | 1302 | Speak to Lee Land about Photoshop configuration settings for Retouchers vs Art Director -- where is this at? | 2013-03-11 | 2013-03-12 |  |  |  |  | 2013-03-11 | 2013-06-27 | EJ/LL |  | Deferred; awaiting list from Lee Land. Since Mac consultant work is complete this will need to be done after the fact as a separate project. | 1035
|  | 1304 | Determine if Depthstar RIP can still be accessed | 2013-03-11 | 2013-03-18 |  |  |  |  | 2013-03-11 | 2013-06-27 | EJ |  | Awaiting response from Tom/Pete. 6/27 still awaiting response, this software has been moved outside the project. | 1037
|  | 1305 | Determine if RIP software is compatible (EFI XF) | 2013-03-11 | 2013-03-18 |  |  |  |  | 2013-03-11 | 2013-03-18 | EJ |  | No issues launching on my machine, awaiting response from Tom/Pete | 1038
|  | 1306 | Determine if RIP software is compatible (Xerox/EFI Fiery Command Workstation) | 2013-03-11 | 2013-03-14 |  |  |  |  | 2013-03-11 | 2013-03-14 | EJ |  | Yes, version 5.4 is compatible. | 1039
|  | 1307 | Determine if NEC ImageExpress will need a new version for Mountain Lion | 2013-03-11 | 2013-03-11 |  |  |  |  | 2013-03-11 | 2013-03-28 | EJ |  | Yes, version 1.2.8 is compatible. | 1040
|  | 1308 | Determine if Xerox EFI Fiery drivers will need a new version for Mountain Lion | 2013-03-11 | 2013-03-11 |  |  |  |  | 2013-03-11 | 2013-03-28 | EJ |  |  | 1041
|  | 1309 | Determine Cisco's recommended version of CUPC/Jabber for Mountain Lion | 2013-02-27 | 2013-02-27 |  |  |  |  | 2013-02-27 | 2013-02-27 | EJ |  | We will continue to use version 7.1.2 as there have been no major issues determined our testing. | 1042
|  | 1310 | Determine if we will need to upgrade VPN client for Mountain Lion -- Call Cisco, what is version of client that supports Mountain Lion? | 2013-02-27 | 2013-02-27 |  |  |  |  | 2013-03-11 | 2013-03-11 | EJ |  | Cisco recommends we upgrade to AnyConnect 3 or use built in VPN client. Discuss with IT Manager. AnyConnect 3 confirmed working. We are licensed and will use AnyConnect 3. | 1043
|  | 1311 | When reimaging an existing system to a newer OS & Centrify version, does anything need to be done with the AD user object? Call Centrify. | 2013-03-11 | 2013-04-19 |  |  |  |  | 2013-03-11 | 2013-04-19 | EJ |  | Existing user object will need to be moved to new OU. | 1044
|  | 1312 | Centrify recommends we use 'automatic' DC setting to allow users that travel to take advantage of the local DC | 2013-03-20 | 2013-03-20 |  |  |  |  | 2013-03-11 | 2013-03-20 | EJ
|  | 1313 | Rename/Create Centrify zone from test3 to Avanti, move existing users in -- Do we need to create a new zone, or can we just rename the existing one? -- Call Centrify. | 2013-03-06 | 2013-03-06 |  |  |  |  | 2013-03-06 | 2013-03-06 | EJ |  | We can rename existing zone, and issue a restart command to Centrify clients. Done. | 1045
|  | 1314 | Designate a single UNIX group for all Avanti mac users, move existing users to this group -- Can this be done without impacting file ownership on the SAN? -- Call Centrify / EMC | 2013-03-11 | 2013-02-28 |  |  |  |  | 2013-03-15 | 2013-03-20 | EJ |  | Group move scheduled for 3/18, group deletion scheduled for 3/20. | 1046
|  | 1315 | Previously Centrify had recommended against using SMB print queues post-version 4.4.0. Is this still the case? If not, how is it implemented? -- Call Centrify | 2013-03-06 | 2013-03-05 |  |  |  |  | 2013-03-06 | 2013-03-05 | EJ |  | This is still the case. | 1047
|  | 1316 | If we can't use SMB queues on the version of Centrify going on the image, use LPD instead -- Implement on AVANTI1 / AVANTITY1 / AVANTINY1 and test. | 2013-03-07 | 2013-03-06 |  |  |  |  | 2013-03-15 | 2013-03-15 | EJ |  | Implemented on all servers; testing on my machine. Test successful; no issues. | 1048
|  | 1317 | Does anything need to be done to enable users to PHD sync when upgrading from Snow Leopard to Mountain Lion? -- Check with Apple / Mac Pros | 2013-03-11 | 2013-03-11 |  |  |  |  | 2013-03-15 | 2013-03-26 | EJ/AP |  | No… no issues with training3 user when logging in; also Apple Engineer consulted is unaware of anything special needing to be done. | 1049
|  | 1318 | Does SyncCheck FTP script work on Mountain Lion? Are XML files readable by SyncCheck? | 2013-02-19 | 2013-02-19 |  |  |  |  | 2013-02-19 | 2013-02-19 | EJ |  | Yes, on both counts -- confirmed by testing on my own laptop and confirming SyncCheck could read the data from all Systems machines | 1050
|  | 1319 | Create spreadsheet list of applications, versions and updates to be deployed | 2013-02-25 | 2013-02-27 |  |  |  |  | 2013-02-25 | 2013-02-27 | EJ |  | Mac_Image_Planning.xlsx | 1051
|  | 1320 | Create spreadsheet list of settings packages for applications to be deployed | 2013-02-25 | 2013-02-27 |  |  |  |  | 2013-02-25 | 2013-02-27 | EJ |  | Mac_Image_Planning.xlsx | 1052
|  | 1321 | NY's Disk Tracker application may not work on Mountain Lion, test. Inform David Laubach and Pete / Liza / Tom Chicoine. | 2013-03-11 | 2013-03-20 |  |  |  |  | 2013-03-11 | 2013-03-20 | EJ |  | Tested; files need to be renamed to .dtc and version 2.4.5 is compatible with Mountain Lion. | 1053
|  | 1322 | Designate install repository on AVANTI8 for standard & nonstandard software for Mac Refresh | 2013-02-25 | 2013-02-27 |  |  |  |  | 2013-02-25 | 2013-02-27 | EJ |  | AVANTI8\Install\Mac\Mac_Refresh | 1054
|  | 1323 | Predownload all standard software for deployment and place in install repository | 2013-03-11 | 2013-03-11 |  |  |  |  | 2013-03-15 | 2013-04-11 | EJ |  |  | 1055
|  | 1324 | Get list of nonstandard software from all machines using AM | 2013-03-11 | 2013-04-24 |  |  |  |  | 2013-03-15 | 2013-04-24 | EJ |  |  | 1056
|  | 1325 | Add nonstandard software to Mac_Image_Planning.xlsx, designate if license deactivation needed, which users' machines it will get installed on | 2013-03-18 | 2013-04-24 |  |  |  |  | 2013-03-18 | 2013-04-24 | EJ |  |  | 1057
|  | 1326 | Confirm with primary user or responsible party the list of nonstandard software | 2013-03-19 | 2013-04-25 |  |  |  |  | 2013-03-22 | 2013-05-24 | EJ |  | Emails sent; awaiting responses. | 1058
|  | 1327 | Confirm compatibility of nonstandard software with Mountain Lion; if new version needed, or if not compatible at all. If not compatible, notify user. | 2013-03-25 | 2013-05-06 |  |  |  |  | 2013-03-27 | 2013-05-24 | EJ |  |  | 1059
|  | 1328 | Determine if we have an installer for a compatible version for each nonstandard software; if not; download and place into repository | 2013-03-27 | 2013-05-06 |  |  |  |  | 2013-03-27 | 2013-05-24 | EJ |  |  | 1060
|  | 1329 | Determine installation procedures for nonstandard software | 2013-03-28 | 2013-05-06 |  |  |  |  | 2013-03-29 | 2013-05-31 | EJ |  |  | 1061
|  | 1330 | What data from Standard Software on a user's machine will not be transferred automatically (Entourage Tasks, Rules, Signature, Mailing Lists)? | 2013-03-18 | 2013-05-06 |  |  |  |  | 2013-03-18 | 2013-05-21 | EJ |  |  | 1062
|  | 1331 | Convey a list of standard software with non-automated data transfer and let them know either how to transfer the data or that the data will need to be reentered | 2013-03-19 | 2013-05-24 |  |  |  |  | 2013-03-19 | 2013-05-24 | EJ |  |  | 1063
1065
| 1400 | Hardware Prerequisites |  | 2013-02-19 | 2013-02-19 |  |  |  |  | 2013-04-25 | 2013-06-27 | EJ |  |  | 1066
1067
|  | 1401 | Will AVANTI19 / 29 support Mountain Lion? | 2013-02-19 | 2013-02-19 |  |  |  |  | 2013-02-19 | 2013-02-19 | EJ |  | AVANTI29 will not support Mountain Lion. AVANTI19 will support Mountain Lion. | 1068
|  | 1402 | Generate spreadsheet of all Mac hardware specs: CPU Cores, CPU GHz, Processor, Memory, Memory Type, HD Size, Scratch Disk Size, Display Model, Display Size | 2013-02-22 | 2013-02-22 |  |  |  |  | 2013-02-22 | 2013-02-22 | EJ |  | Mac_Refresh_Hardware_Purchases.xlsx | 1069
|  | 1403 | Review Mac hardware spread sheet with IT manager to revise standard hardware specs, determine test specs for Photoshop class machines | 2013-02-22 | 2013-02-22 |  |  |  |  | 2013-02-22 | 2013-02-22 | EJ/SWL |  |  | 1070
|  | 1404 | Determine with Mac Pros what machines will need upgrades -- Send updated list of Macs | 2013-03-08 | 2013-03-08 |  |  |  |  | 2013-03-08 | 2013-03-08 | EJ/MP |  |  | 1071
|  | 1405 | Order test hardware for Photoshop class machines | 2013-03-05 | 2013-03-05 |  |  |  |  | 2013-03-05 | 2013-03-05 | EJ |  |  | 1072
|  | 1406 | Once hardware received; install in test Mac Pro | 2013-03-18 | 2013-03-25 |  |  |  |  | 2013-03-18 | 2013-03-25 | EJ |  | Awaiting availability of test system from Dave Phipps | 1073
|  | 1407 | Prep test Mac Pro for use - Install standard software manually, configure manually | 2013-03-18 | 2013-03-25 |  |  |  |  | 2013-03-18 | 2013-04-24 | EJ |  | Awaiting availability of test system from Dave Phipps | 1074
|  |  | Touch base with Photoshop test user and confirm machine switch date | 2013-03-27 | 2013-03-27 |  |  |  |  | 2013-03-29 | 2013-04-24 |  |  | Emailed Lee Land, awaiting response.
|  | 1408 | Photoshop class test user performs test. Based on Photoshop class machine test, revise or confirm Mac hardware specs | 2013-03-19 | 2013-04-24 |  |  |  |  | 2013-03-29 | 2013-04-24 | EJ/SWL |  |  | 1075
|  | 1409 | What existing hardware that is not being used can we use to upgrade outdated Macs? | 2013-02-22 | 2013-02-22 |  |  |  |  | 2013-02-22 | 2013-02-22 | EJ |  | None of our existing spare hardware can be used for this. | 1076
|  | 1410 | Determine 1 desktop and 1 laptop that will be replaced; order these first so we have machines to test on and create images on. | 2013-03-22 | 2013-03-22 |  |  |  |  | 2013-03-22 | 2013-04-01 | EJ |  | Machines ordered; will go to Aubrey Stalnaker and Pete Pultz. | 1077
|  | 1411 | Create spreadsheet of machine upgrades and accessories needing to be purchased | 2013-03-11 | 2013-03-11 |  |  |  |  | 2013-03-11 | 2013-03-11 | EJ |  | Mac_Refresh_Hardware_Purchases.xlsx | 1078
|  | 1412 | Put together quote request for systems, accessories and licenses necessary for upgrades and send to Mac Pros, also spare mac laptop and spare mac desktop | 2013-03-20 | 2013-03-20 |  |  |  |  | 2013-04-03 | 2013-04-19 | EJ |  | We will be purchasing most hardware directly from Apple; anything we can't purchase from Apple will come from Mac Pros | 1079
|  | 1413 | Designate temporary area in server room for decommissioned systems / accessories | 2013-02-26 | 2013-02-26 |  |  |  |  | 2013-02-26 | 2013-02-26 | EJ |  | Decommissioned systems will go in the server room closet. | 1080
|  | 1414 | Place order with Mac Professionals | 2013-04-04 | 2013-04-04 |  |  |  |  | 2013-04-05 | 2013-04-05 | EJ/MP |  | We will not be ordering from Mac Pros. | 1081
|  | 1415 | Place order with Apple | 2013-04-04 | [5 empty] | 2013-04-05 |  | EJ |  | Order placed. | 1082
|  | 1416 | Designate storage area in server room for new hardware | 2013-02-26 | 2013-02-26 |  |  |  |  | 2013-02-26 | 2013-02-26 | EJ |  | New hardware will go off to the side in the server room; near the entrance and near the rear wall. | 1083
|  | 1417 | Clean up server room to maximize space for received/decommissioned items | 2013-03-18 | [5 empty] | 2013-04-01 |  | EJ |  |  | 1084
|  | 1418 | Confirm all items received | 2013-04-24 | 2013-05-03 |  |  |  |  | 2013-04-24 | 2013-05-03 | EJ/MP |  | Stan confirmed. KEEP ALL BOXES UNTIL CLEANUP/CLOSE | 1085
|  | 1419 | Confirm all systems and attached displays entered into AppleCare | 2013-04-25 | 2013-04-25 |  |  |  |  | 2013-04-25 | 2013-06-26 | EJ/MP |  |  | 1086
|  | 1420 | Confirm all Quadro graphics cards registered with PNY | 2013-05-06 | 2013-05-06 |  |  |  |  | 2013-05-06 | 2013-06-27 | EJ/MP
1087
| 1500 | Notable Dates |  | 2013-03-01 | 2013-03-01 |  |  |  |  | 2013-05-20 | 2013-05-20 | EJ |  |  | 1088
1089
|  | 1501 | Shane Vacation | 2013-03-01 | 2013-03-01 |  |  |  |  | 2013-03-08 | 2013-03-08 | SWL |  |  | 1090
|  | 1502 | Erik Vacation | 2013-04-26 | 2013-04-26 |  |  |  |  | 2013-05-03 | 2013-05-03 | EJ |  |  | 1091
|  | 1503 | Stan Vacation | 2013-05-16 | 2013-05-16 |  |  |  |  | 2013-05-21 | 2013-05-21 | SJL |  |  | 1092
1093
2000 | Image Development |  |  | 2013-03-05 | 2013-02-27 |  |  |  |  | 2013-04-23 | 2013-07-12 | EJ |  |  | 1094
1095
| 2100 | Deployment / Update Server Setup (AVANTI19) |  | 2013-03-05 | 2013-03-05 |  |  |  |  | 2013-04-15 | 2013-05-23 | EJ |  |  | 1096
1097
|  | 2101 | Move master distribution point for Absolute Manage to AVANTI29 prior to AVANTI19 upgrade, get approval from IT Manager | 2013-03-05 | 2013-03-05 |  |  |  |  | 2013-03-05 | 2013-03-05 | EJ/SL |  | Once approved by IT Manager, make AVANTI29 a distribution point and allow it to transfer updates/packages over the weekend. | 1098
|  | 2102 | Set up SUS on AVANTI29 prior to AVANTI19 upgrade | 2013-03-05 | 2013-03-05 |  |  |  |  | 2013-03-05 | 2013-03-05 | EJ |  |  | 1099
|  | 2103 | Setup AAMEE on AVANTI29 prior to AVANTI19 upgrade | 2013-03-11 | 2013-03-19 |  |  |  |  | 2013-03-11 | 2013-03-19 | EJ |  | AAMEE - Adobe Application Manager Enterprise Edition, for creating Creative Suite updates packages. | 1100
|  | 2104 | Create Centrify test group policy to point updates to AVANTI29 | 2013-03-15 | 2013-04-09 |  |  |  |  | 2013-03-15 | 2013-04-09 | EJ |  |  | 1101
|  | 2105 | Test group policy on DTDE0160 -- Can it see updates, can it download updates, can it apply updates? | 2013-03-18 | 2013-04-09 |  |  |  |  | 2013-03-18 | 2013-04-09 | EJ |  | No issues. | 1102
|  | 2106 | Create disk image backups of both AVANTI19 volumes prior to upgrade | 2013-03-14 | 2013-04-09 |  |  |  |  | 2013-03-14 | 2013-04-09 | EJ |  | We will not be using AVANTI19 as the server as we experienced disk I/O errors when attempting to back up. | 1103
|  | 2107 | Make old images available on AVANTI8 for manual imaging using bootable OS X CD & external HD, if necessary | 2013-03-15 | 2013-04-09 |  |  |  |  | 2013-03-15 | 2013-04-09 | EJ |  | We will not be using AVANTI19 as the server as we experienced disk I/O errors when attempting to back up. | 1104
|  | 2108 | Work with Mac Pros to configure and set up Mountain Lion server for image deployment and SUS, document process. | 2013-04-15 | 2013-04-15 |  |  |  |  | 2013-04-15 | 2013-04-15 | EJ/MP |  | Tentative - pending confirmation from Mac Pros | 1105
|  | 2109 | Create and test netboot image for Snow Leopard | 2013-04-15 | 2013-04-15 |  |  |  |  | 2013-04-15 | 2013-04-15 | EJ/MP |  | We will not need a Snow Leopard image. | 1106
|  | 2110 | Create and test netboot image for Mountain Lion | 2013-04-15 | 2013-04-15 |  |  |  |  | 2013-04-15 | 2013-04-15 | EJ/MP |  | Tentative - pending confirmation from Mac Pros | 1107
|  | 2111 | Create and test a simple test image for Mountain Lion (create image of base OS using DeployStudio, create a test deployment .pkg and a test script, attempt to deploy) | 2013-04-15 | 2013-04-15 |  |  |  |  | 2013-04-15 | 2013-04-15 | EJ/MP |  | Tentative - pending confirmation from Mac Pros. This is not the full image, just a simple clone and deploy using DeployStudio to confirm the deployment process works. | 1108
|  | 2112 | Test deployment of a preexisting Snow Leopard image | 2013-04-15 | 2013-04-15 |  |  |  |  | 2013-04-15 | 2013-04-15 | EJ/MP |  | Not necessary. The old AVANTI19 will be kept. | 1109
|  | 2113 | Modify Systems' machines' group policy to point to Mountain Lion server for updates, for testing | 2013-04-15 | 2013-05-21 |  |  |  |  | 2013-04-15 | 2013-05-21 | EJ |  |  | 1110
|  | 2114 | Test deployment of updates to Systems machines using Absolute Manage | 2013-04-15 | 2013-05-21 |  |  |  |  | 2013-04-15 | 2013-05-21 | EJ |  |  | 1111
|  | 2115 | Modify test policy for DTDE0160 to point to Mountain Lion server for updates | 2013-04-15 | 2013-05-23 |  |  |  |  | 2013-04-15 | 2013-05-23 | EJ |  |  | 1112
|  | 2116 | Test group policy on DTDE00160 -- Can it see updates, can it download updates, can it apply updates? | 2013-04-15 | 2013-05-23 |  |  |  |  | 2013-04-15 | 2013-05-23 | EJ |  |  | 1113
|  | 2117 | Modify all users' machines' group policy to point to Mountain Lion server for updates | 2013-04-15 | 2013-05-23 |  |  |  |  | 2013-04-15 | 2013-05-23 | EJ |  |  | 1114
1115
| 2200 | Group Policy Setup / Planning |  | 2013-03-11 | 2013-02-27 |  |  |  |  | 2013-05-13 | 2013-07-12 | EJ |  |  | 1116
1117
|  | 2201 | Create spreadsheet to track preexisting and new group policies | 2013-03-11 | 2013-02-27 |  |  |  |  | 2013-03-11 | 2013-02-27 | EJ |  | Mac_Image_Planning.xlsx | 1118
|  | 2202 | Can we upgrade console on AVANTI2 to 5.1 without impacting 4.4.0 clients? Call Centrify. | 2013-03-11 | 2013-02-22 |  |  |  |  | 2013-03-11 | 2013-02-22 | EJ |  | We can upgrade to 5.1 console without impacting 4.4.0 clients, per Brian | 1119
|  | 2203 | Remove Centrify 4.4.0 Console from AVANTI2, install Centrify 5.1 Console | 2013-03-11 | 2013-02-27 |  |  |  |  | 2013-03-11 | 2013-02-27 | EJ |  | Done. | 1120
|  | 2204 | Install new Centrify Client (5.1) on Systems Macs for test -- Confirm 'password expiration bug' is resolved | 2013-03-11 | 2013-03-01 |  |  |  |  | 2013-03-11 | 2013-07-12 | EJ |  | Stan and Erik currently using Centrify 5.1 If not resolved; call Centrify and resolve before proceeding (this may affect RR). Update 3/14 -- Tested… this is not resolved. Emailed Centrify support. Update 3/19, this has gone to Centrify engineering for diagnosis. Update 5/31, this is still at Centrify engineering. Update 6/27, Centrify recommends we recreate the account as this should resolve the issue. Update 7/12 -- We are no longer experiencing these messages. | 1121
|  | 2205 | Examine existing group policies. Are there any settings we would want to change? | 2013-03-12 | 2013-04-19 |  |  |  |  | 2013-03-12 | 2013-04-19 | EJ |  | Trim 'sync' list -- Remove Application Support, Preferences, ensure ONLY requested synced folders are synced. | 1122
|  | 2206 | Determine new group policies since DirectControl 4.4.0. Are there any new policies we would want to make use of? | 2013-03-13 | 2013-04-19 |  |  |  |  | 2013-03-13 | 2013-04-19 | EJ |  |  | 1123
|  | 2207 | Once group policies updated; test all policies being applied and make sure it is working properly | 2013-03-14 | 2013-04-19 |  |  |  |  | 2013-03-14 | 2013-04-19 | EJ |  | Log any issues to Mac_Image_Planning.xlsx | 1124
|  | 2208 | Create test OUs for image development machines | 2013-04-03 | 2013-04-03 |  |  |  |  | 2013-04-03 | 2013-04-03 | EJ |  | Tests created for laptop and desktop in DT and NY
|  | 2209 | Determine how we will transition users/computers between upgrades | 2013-04-10 | 2013-04-10 |  |  |  |  | 2013-04-10 | 2013-04-10 | EJ |  | Users/computers will be moved to temporary OU as they are upgraded. When user machine upgrades are complete; preexisting OUs will be renamed, and new OUs renamed to same name as old OUs.
|  | 2210 | Create group policies in new OUs | 2013-05-06 | 2013-05-06 |  |  |  |  | 2013-05-13 | 2013-05-21 | EJ
|  | 2211 | Create group policies for NY Community Workstations (Image Viewing, Conf Room, Hotelling Workstation) | 2013-06-12 | 2013-06-12 |  |  |  |  | 2013-06-14 | 2013-06-14 | EJ
1125
| 2300 | OS and Application Settings Planning |  | 2013-03-15 | 2013-02-27 |  |  |  |  | 2013-04-05 | 2013-05-06 | EJ |  |  | 1126
1127
|  | 2301 | Create spreadsheet list of issues and individual settings for applications | 2013-03-15 | 2013-02-27 |  |  |  |  | 2013-03-15 | 2013-02-27 | EJ |  | Mac_Image_Planning.xlsx | 1128
|  | 2302 | Determine standard settings for Mac OS X and Mac OS X standard apps, and their deployment method | 2013-03-18 | 2013-03-27 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  | Check documentation for any useful or new features that might be beneficial | 1129
|  | 2303 | Determine standard settings for Microsoft Outlook 2011, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  | We will be using name & password auth, not Kerberos. | 1130
|  | 2304 | Determine standard settings for Microsoft Excel 2011, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  | Check documentation for any useful or new features that might be beneficial | 1131
|  | 2305 | Determine standard settings for Microsoft Word 2011, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  | Check documentation for any useful or new features that might be beneficial | 1132
|  | 2306 | Determine standard settings for Microsoft Powerpoint 2011, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  | Check documentation for any useful or new features that might be beneficial | 1133
|  | 2307 | Determine standard settings for Safari, and their deployment method | 2013-03-18 | 2013-03-27 |  |  |  |  | 2013-03-29 | 2013-03-27 | EJ |  |  | 1134
|  | 2308 | Determine standard settings for FileMaker Pro 11, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  |  | 1135
|  | 2309 | Determine standard settings for FileZilla, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  |  | 1136
|  | 2310 | Determine standard settings iTerm, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  | Use iTerm | 1137
|  | 2311 | Determine standard settings for Centrify DirectControl, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  | Check documentation for any useful or new features that might be beneficial | 1138
|  | 2312 | Determine if standard settings for Photoshop CS6 / other CS6 apps can be deployed | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-18 | 2013-03-18 | EJ |  | Deferred; awaiting list from Lee Land. Since Mac consultant work is complete this will need to be done after the fact as a separate project. | 1139
|  | 2313 | Determine standard settings for CUPC/Jabber, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  | Check documentation for any useful or new features that might be beneficial | 1140
|  | 2314 | Determine standard settings for Sophos Anti-virus, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-01 | EJ |  | Deployed via Console | 1141
|  | 2315 | Determine standard settings for Universal Type Client, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  |  | 1142
|  | 2316 | Determine standard settings for Absolute Manage Client, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  |  | 1143
|  | 2317 | Determine standard settings for i1Profiler, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  |  | 1144
|  | 2318 | Determine standard settings for VPN Client, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  | Check documentation for any useful or new features that might be beneficial | 1145
|  | 2319 | Determine standard settings for NEC ImageExpress, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  |  | 1146
|  | 2320 | Determine standard settings for Wacom Tablet Driver, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-01 | EJ |  | Allow users to set their own preferences | 1147
|  | 2321 | Determine standard settings for all print drivers -- Bizhub 501, C353, Xerox, Epson, HPLJ4700, HPLJ4200, Training Room, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  |  | 1148
|  | 2323 | Determine any desktop-specific settings, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  |  | 1150
|  | 2324 | Determine any laptop-specific settings, and their deployment method | 2013-03-18 | 2013-03-28 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  | ImageExpress deployment and VPN deployment | 1151
|  | 2325 | Confirm settings are appropriate with Systems | 2013-04-01 | 2013-04-25 |  |  |  |  | 2013-04-01 | 2013-05-06 | EJ/SYS |  | Testing in progress. | 1152
|  | 2326 | Confirm standard settings for Alpha Config for OS and Applications complete - All settings/issues resolved or deferred in spreadsheet. | 2013-04-02 | 2013-04-02 |  |  |  |  | 2013-04-05 | 2013-05-06 | EJ |  | Mac_Image_Planning.xlsx | 1153
|  | 2327 | Confirm how to prevent old settings from transferring / being synced | 2013-03-18 | 2013-04-19 |  |  |  |  | 2013-03-29 | 2013-04-19 | EJ |  | New sync settings will prevent unwanted files from syncing to computer. | 1154
1155
| 2400 | Image and Process Creation |  | 2013-04-16 | 2013-04-16 |  |  |  |  | 2013-04-23 | 2013-05-23 | EJ |  |  | 1156
1157
|  | 2401 | Create Post Image Configuration document; any changes that must be implemented manually post-deployment of image, apps and settings should be included/logged. | 2013-04-16 | 2013-04-16 |  |  |  |  | 2013-04-16 | 2013-04-16 | EJ |  |  | 1158
|  | 2402 | Work with Mac Pros to design standard base image for laptop and desktop | 2013-04-16 | 2013-04-16 |  |  |  |  | 2013-04-19 | 2013-04-19 | EJ/MP |  |  | 1159
|  | 2403 | Work with Mac Pros to create deployment packages for applications and settings | 2013-04-16 | 2013-04-16 |  |  |  |  | 2013-04-18 | 2013-04-18 | EJ/MP |  |  | 1160
|  | 2404 | Work with Mac Pros to create deployment packages for all printers and determined settings -- Bizhub 501, C353, Xerox, Epson, HPLJ4700, HPLJ4200, Training Room | 2013-04-16 | 2013-04-16 |  |  |  |  | 2013-04-17 | 2013-04-16 | EJ/MP |  |  | 1161
|  | 2405 | Determine standard process for image deployment to new machines with preexisting users; document it | 2013-04-19 | 2013-04-19 |  |  |  |  | 2013-04-19 | 2013-04-19 | EJ/MP |  | Process should include completing and confirming a successful sync before image deployment taking place. | 1162
|  | 2406 | Determine standard process for image deployment to existing machines with preexisting users; document it | 2013-04-19 | 2013-04-19 |  |  |  |  | 2013-04-19 | 2013-04-19 | EJ/MP |  | Process should include completing and confirming a successful sync before image deployment taking place. | 1163
|  | 2407 | Determine standard process for image deployment to machines with new users, document it | 2013-04-19 | 2013-04-19 |  |  |  |  | 2013-04-19 | 2013-04-19 | EJ/MP |  |  | 1164
|  | 2408 | Determine OS / Application update process for updated configuration, if there are any changes | 2013-04-23 | 2013-05-22 |  |  |  |  | 2013-04-23 | 2013-05-22 | EJ/MP |  | Same as existing process; but use separate group in Absolute Manage. | 1165
|  | 2409 | Determine process to update images and deployment packages going forward, document it | 2013-04-23 | 2013-05-23 |  |  |  |  | 2013-04-23 | 2013-05-23 | EJ/MP |  |  | 1166
|  | 2410 | Determine standard process for purchasing machines, document it | 2013-04-23 | 2013-05-23 |  |  |  |  | 2013-04-23 | 2013-05-23 | EJ |  |  | 1167
|  | 2411 | Determine standard process for decommissioning machines, document it | 2013-04-23 | 2013-05-23 |  |  |  |  | 2013-04-23 | 2013-05-23 | EJ/MP |  |  | 1168
1169
3000 | Image Testing |  |  | 2013-04-22 | 2013-04-22 |  |  |  |  | 2013-05-24 | 2013-05-30 | EJ |  |  | 1170
1171
| 3100 | Image Testing |  | 2013-04-22 | 2013-04-22 |  |  |  |  | 2013-05-24 | 2013-05-30 | EJ |  |  | 1172
1173
|  | 3101 | Design test process/checklist; cover both new user installs and existing user installs | 2013-04-22 | 2013-04-19 |  |  |  |  | 2013-04-22 | 2013-04-19 | EJ |  |  | 1174
|  | 3102 | Deploy draft image(s) to test desktop and laptop machines | 2013-04-23 | 2013-04-19 |  |  |  |  | 2013-04-23 | 2013-04-19 | EJ |  |  | 1175
|  | 3103 | Perform deployment process (existing machine, existing user) and complete test process/checklist | 2013-04-23 | 2013-04-19 |  |  |  |  | 2013-04-23 | 2013-04-19 | EJ |  | Log issues, errors and settings changes to Mac_Image_Planning.xlsx | 1176
|  | 3104 | Perform deployment process (new machine, existing user) and complete test process/checklist | 2013-04-23 | 2013-04-19 |  |  |  |  | 2013-04-23 | 2013-04-19 | EJ |  | Log issues, errors and settings changes to Mac_Image_Planning.xlsx | 1177
|  | 3105 | Perform deployment process (new machine, new user) and complete test process/checklist | 2013-04-23 | 2013-04-23 |  |  |  |  | 2013-04-23 | 2013-04-23 | EJ |  | Log issues, errors and settings changes to Mac_Image_Planning.xlsx | 1178
|  | 3106 | Deploy draft image(s) to one or more Systems users, perform deployment process, complete test process/checklist | 2013-04-24 | 2013-04-23 |  |  |  |  | 2013-04-24 | 2013-04-23 | EJ |  | Log issues, errors and settings changes to Mac_Image_Planning.xlsx | 1179
|  | 3107 | Work with Mac Pros to implement necessary changes to image / deployment packages determined from Alpha configuration testing | 2013-05-06 | 2013-05-14 |  |  |  |  | 2013-05-06 | 2013-05-14 | EJ/MP |  |  | 1180
|  | 3108 | Create Beta configuration based on changes, update spreadsheet | 2013-05-06 | 2013-05-14 |  |  |  |  | 2013-05-06 | 2013-05-14 | EJ/MP |  |  | 1181
|  | 3109 | Deploy Beta configuration to 1-2 users from each department of Creative, Design and Production, following deployment process and completing test process/checklist. Users test. | 2013-05-07 | 2013-05-06 |  |  |  |  | 2013-05-17 | 2013-05-06 | EJ |  | Alpha configuration deployed to these test users. Beta configuration changes only affect post-config; and thus will not impact users, only how Systems deploys machines. Beta configuration changes tested by Erik. | 1182
|  | 3110 | Work with Mac Pros to implement necessary changes to image / deployment packages determined from Beta configuration testing | 2013-05-20 | 2013-05-20 |  |  |  |  | 2013-05-20 | 2013-05-20 | EJ/MP |  |  | 1183
|  | 3111 | Create Release/Production configuration based on changes, update spreadsheet | 2013-05-20 | 2013-05-14 |  |  |  |  | 2013-05-20 | 2013-05-20 | EJ/MP |  |  | 1184
|  | 3112 | Reimage Beta configuration machines with Release/Production configuration, and perform final test, following deployment process and completing test process/checklist | 2013-05-21 | 2013-05-30 |  |  |  |  | 2013-05-23 | 2013-05-30 | EJ |  | All testing complete. Image is now considered production. | 1185
|  | 3113 | Confirm image testing is complete; and all issues/settings changes in spreadsheet have been either resolved or deferred before proceeding to Image Deployment. | 2013-05-24 | 2013-05-30 |  |  |  |  | 2013-05-24 | 2013-05-30 | SYS/MP |  | All issues/settings resolved/deferred. | 1186
1187
4000 | Image Deployment and Training |  |  | 2013-04-01 | 2013-04-01 |  |  |  |  | 2013-07-12 | 2013-07-30 | EJ |  |  | 1188
1189
| 4100 | Image Deployment and Training |  | 2013-04-01 | 2013-04-01 |  |  |  |  | 2013-07-12 | 2013-07-30 | EJ |  |  | 1190
1191
|  | 4101 | Create training Materials for Office 2011 | 2013-04-01 | 2013-04-01 |  |  |  |  | 2013-04-01 | 2013-05-30 | EJ |  |  | 1192
|  | 4102 | Create training materials for Mac OS X 10.8 | 2013-04-02 | 2013-04-02 |  |  |  |  | 2013-04-02 | 2013-05-30 | EJ |  |  | 1193
|  | 4103 | Create training materials for CUPC / Jabber (if updated) | 2013-04-03 | 2013-04-03 |  |  |  |  | 2013-04-03 | 2013-04-03 | EJ |  | Not updated. | 1194
|  | 4104 | Create training materials for VPN client (if updated) | 2013-04-03 | 2013-04-03 |  |  |  |  | 2013-04-03 | 2013-05-30 | EJ |  |  | 1195
|  | 4105 | Double check training / deployment scheduling with IT Manager | 2013-04-25 | 2013-04-25 |  |  |  |  | 2013-05-06 | 2013-04-30 | EJ
|  | 4106 | Scheduled training and deployment for Group 1 users; confirmed with dept. heads | 2013-04-08 | 2013-05-15 |  |  |  |  | 2013-04-08 | 2013-05-24 | EJ |  |  | 1196
|  | 4107 | "Information" section in Mac Refresh Deployment Checklist completed for Group 1 | 2013-04-08 | 2013-05-24 |  |  |  |  | 2013-04-08 | 2013-05-24 | EJ |  |  | 1197
|  | 4108 | Scheduled training and deployment for Group 2 users; confirmed with dept. heads | 2013-04-08 | 2013-05-15 |  |  |  |  | 2013-04-08 | 2013-05-24 | EJ |  |  | 1198
|  | 4109 | "Information" section in Mac Refresh Deployment Checklist completed for Group 2 | 2013-04-08 | 2013-05-24 |  |  |  |  | 2013-04-08 | 2013-05-24 | EJ |  |  | 1199
|  | 4110 | Scheduled training and deployment for Group 3 users; confirmed with dept heads | 2013-04-08 | 2013-05-15 |  |  |  |  | 2013-04-08 | 2013-05-24 | EJ |  | Betsy will need manual rescheduling. | 1200
|  | 4111 | "Information" section in Mac Refresh Deployment Checklist completed for Group 3 | 2013-04-08 | 2013-05-24 |  |  |  |  | 2013-04-08 | 2013-05-24 | EJ |  | Betsy will need manual rescheduling. | 1201
|  | 4112 | Scheduled training and deployment for Group 4 users; confirmed with dept. heads | 2013-04-08 | 2013-05-15 |  |  |  |  | 2013-04-08 | 2013-05-24 | EJ |  |  | 1202
|  | 4113 | Schedule flight and hotel stay for Systems in NY | 2013-04-08 | 2013-06-14 |  |  |  |  | 2013-04-08 | 2013-06-25 | EJ |  |  | 1203
|  | 4114 | "Information" section in Mac Refresh Deployment Checklist completed for Group 4 | 2013-04-08 | 2013-05-30 |  |  |  |  | 2013-04-08 | 2013-05-30 | EJ |  |  | 1204
|  | 4115 | Shipping manifest created for NY hardware upgrades, replacement machines, and replacement accessories | 2013-04-08 | 2013-06-18 |  |  |  |  | 2013-04-08 | 2013-06-18 | EJ |  |  | 1205
|  | 4116 | Shipped NY hardware upgrades, replacement machines and replacement accessories to NY | 2013-06-20 | 2013-06-20 |  |  |  |  | 2013-06-28 | 2013-06-26 | EJ |  |  | 1206
|  | 4117 | Confirmed NY received all items listed on shipping manifest | 2013-07-01 | 2013-06-26 |  |  |  |  | 2013-07-03 | 2013-06-27 | EJ |  | Awaiting confirmation from Dave L | 1207
|  | 4118 | Schedule use of training room on training dates | 2013-04-08 | 2013-04-25 |  |  |  |  | 2013-04-08 | 2013-04-25 | EJ |  | Scheduled tentative dates | 1208
|  | 4119 | Group 1 replacement machines base configuration deployed | 2013-05-31 | 2013-05-31 |  |  |  |  | 2013-05-31 | 2013-05-31 | EJ/SYS |  |  | 1209
|  | 4120 | Group 1 trained | 2013-05-31 | 2013-05-31 |  |  |  |  | 2013-05-31 | 2013-05-31 | EJ |  | Friday morning | 1210
|  | 4121 | Group 1 deployed ("Deployment" and "Turnover to User" sections in Mac Refresh Deployment Checklist completed) | 2013-05-31 | 2013-05-31 |  |  |  |  | 2013-06-03 | 2013-06-03 | EJ/SYS |  | Saturday through Monday morning | 1211
|  | 4122 | Group 2 replacement machines base configuration deployed | 2013-06-07 | 2013-06-07 |  |  |  |  | 2013-06-07 | 2013-06-07 | EJ/SYS |  | Friday | 1212
|  | 4123 | Group 2 trained | 2013-06-10 | 2013-06-10 |  |  |  |  | 2013-06-10 | 2013-06-10 | EJ |  | Monday morning | 1213
|  | 4124 | Group 2 deployed ("Deployment" and "Turnover to User" sections in Mac Refresh Deployment Checklist completed) | 2013-06-10 | 2013-06-10 |  |  |  |  | 2013-06-11 | 2013-06-10 | EJ/SYS |  | Monday afternoon/evening through Tuesday morning | 1214
|  | 4125 | Group 3 replacement machines base configuration deployed | 2013-06-14 | 2013-06-14 |  |  |  |  | 2013-06-14 | 2013-06-14 | EJ/SYS |  | Friday | 1215
|  | 4126 | Group 3 trained | 2013-06-17 | 2013-06-17 |  |  |  |  | 2013-06-17 |  | EJ |  | Monday Morning | 1216
|  | 4127 | Group 3 deployed ("Deployment" and "Turnover to User" sections in Mac Refresh Deployment Checklist completed) | 2013-06-17 | 2013-06-17 |  |  |  |  | 2013-06-18 | 2013-06-18 | EJ/SYS |  | Monday afternoon/evening through Tuesday morning | 1217
|  | 4128 | Group 4 replacement machines base configuration deployed | 2013-06-19 | 2013-06-19 |  |  |  |  | 2013-06-19 | 2013-06-21 | EJ/SYS |  |  | 1218
|  | 4129 | Group 4 trained | 2013-07-08 | 2013-07-08 |  |  |  |  | 2013-07-08 | 2013-07-08 | EJ |  | Monday Morning | 1219
|  | 4130 | Group 4 deployed ("Deployment" and "Turnover to User" sections in Mac Refresh Deployment Checklist completed) | 2013-07-08 | 2013-07-08 |  |  |  |  | 2013-07-09 | 2013-07-09 | EJ/SYS |  | Monday afternoon/evening through Tuesday morning | 1220
|  | 4131 | NY Multiuser workstations deployed | 2013-07-09 | 2013-07-09 |  |  |  |  | 2013-07-12 | 2013-07-09 | EJ/SYS |  | Tuesday after user workstations complete | 1221
|  | 4132 | Package up and ship decommissioned items back to Detroit | 2013-07-09 | 2013-07-10 |  |  |  |  | 2013-07-12 | 2013-07-10 | EJ/SYS |  |  | 1222
|  | 4133 | Detroit Multiuser workstations deployed | 2013-06-02 | 2013-07-03 |  |  |  |  | 2013-07-12 | 2013-07-03 | EJ/SYS |  | DTDQ0025 in Dave P's possession, deferred outside of project. Will upgrade as soon as he is done with it.
|  | 4134 | Rescheduled with users requiring manual reschedule | 2013-06-02 | 2013-07-10 |  |  |  |  | 2013-07-12 | 2013-07-10 | EJ/SYS |  | Betsy rescheduled for week of 7/15.
|  | 4135 | Manually rescheduled users trained | 2013-06-02 | 2013-07-10 |  |  |  |  | 2013-07-12 | 2013-07-26 | EJ/SYS
|  | 4136 | Manually rescheduled users deployed | 2013-06-02 | 2013-07-10 |  |  |  |  | 2013-07-12 |  | EJ/SYS
1223
5000 | Cleanup / Close |  |  | 2013-07-15 | 2013-05-31 |  |  |  |  | 2013-08-02 | 2013-07-12 | EJ |  |  | 1224
1225
| 5100 | Cleanup / Close |  | 2013-07-15 | 2013-05-31 |  |  |  |  | 2013-08-02 | 2013-07-12 | EJ |  |  | 1226
1227
|  | 5101 | Determine new location for decommissioned machines / accessories | 2013-07-15 | [5 empty] | 2013-07-19 |  | SYS |  | Removed from project; Systems will tackle cleanup as a separate project. | 1228
|  | 5102 | Determine # of hard drives / laptops / desktops that need to be destroyed | 2013-07-15 | [5 empty] | 2013-07-19 |  | EJ |  | Removed from project; Systems will tackle cleanup as a separate project. | 1229
|  | 5103 | Schedule GEEP pickup of decommissioned machines / accessories | 2013-07-15 | [5 empty] | 2013-07-19 |  | EJ |  | Removed from project; Systems will tackle cleanup as a separate project. | 1230
|  | 5104 | GEEP picks up all decommissioned items | 2013-07-22 | [5 empty] | 2013-07-22 |  | SYS/G |  | Removed from project; Systems will tackle cleanup as a separate project. | 1231
|  | 5105 | Confirm # of hard drives / laptops /desktops destroyed with GEEP | 2013-07-23 | [5 empty] | 2013-08-02 |  | EJ |  | Removed from project; Systems will tackle cleanup as a separate project. | 1232
|  | 5106 | Schedule other systems personnel attempt to deploy the next new machine, to test process and documentation clarity | 2013-07-15 | 2013-05-31 |  |  |  |  | 2013-07-15 | 2013-05-31 | SYS |  |  | 1233
|  | 5107 | Schedule other systems personnel attempt to update the image, to test process and documentation clarity | 2013-07-15 | 2013-07-12 |  |  |  |  | 2013-07-15 | 2013-07-12 | SYS |  |  | 1234
|  | 5108 | Schedule other systems personnel attempt to update the application and settings deployment, to test process and documentation clarity | 2013-07-15 | 2013-07-12 |  |  |  |  | 2013-07-15 | 2013-07-12 | SYS |  |  | 1235