## Project Plan
Avanti Press, Inc.
Mac Refresh Project Plan |  |  |  |  | % Completed | [5 empty] | Responsibility
WBS | Description | Target Start | Assumptions | Actual Start | 25 | 50 | 75 | 100 | Target Finish | Actual Finish | Primary | Man Hours | Comments | Column2 | Section
| Move decommissioned machines / accessories to 5th floor | [13 empty] | Cleanup / Close
| Determine # of hard drives / laptops / desktops that need to be destroyed | [13 empty] | Cleanup / Close
| Schedule GEEP pickup of 5th floor items | [13 empty] | Cleanup / Close
| Confirm # of hard drives / laptops /desktops destroyed with GEEP | [13 empty] | Cleanup / Close
| Designate temporary area in server room for decommissioned systems / accessories | [13 empty] | Cleanup / Close
| Deploy configuration to Group 1 | 2013-05-20 | [6 empty] | 2013-05-24 |  |  |  | Post deployment, a brief orientation session should be given to each user so they know where to find network resources and |  | Image Deployment
| Deploy configuration to Group 2 | 2013-06-03 | [6 empty] | 2013-06-07 | [5 empty] | Image Deployment
| Deploy configuration to Group 3 | 2013-06-17 | [6 empty] | 2013-06-21 | [5 empty] | Image Deployment
| Deploy configuration NY users | 2013-07-01 | [6 empty] | 2013-07-03 | [5 empty] | Image Deployment
| Standard Settings for Alpha Config for OS and Applications complete | [13 empty] | Image Development
| Determine if NEC ImageExpress will need a new version for Mountain Lion | [13 empty] | Image Development
| Determine if Xerox EFI Fiery drivers will need a new version for Mountain Lion | [13 empty] | Image Development
| Determine if we will need to upgrade VPN client for Mountain Lion | [13 empty] | Image Development
| Deployment packages for all printers created; added to deployment procedure | [13 empty] | Image Development
| Rename Centrify zone from test3 to Avanti, move existing users in | [13 empty] | Image Development
| Designate a single UNIX group for all Avanti mac users, move existing users to this group | [13 empty] | Image Development
| Determine standard settings for Mac OS X and Mac OS X standard apps | [13 empty] | Image Development
| Determine standard settings for Microsoft Outlook 2011 | [13 empty] | Image Development
| Determine standard settings for Microsoft Excel 2011 | [13 empty] | Image Development
| Determine standard settings for Microsoft Word 2011 | [13 empty] | Image Development
| Determine standard settings for Microsoft Powerpoint 2011 | [13 empty] | Image Development
| Determine standard settings for Safari | [13 empty] | Image Development
| Determine standard settings for FileMaker Pro 11 | [13 empty] | Image Development
| Determine standard settings for FileZilla | [13 empty] | Image Development
| Determine standard settings 9edge / Terminal | [13 empty] | Image Development
| Determine standard settings for Centrify DirectControl | [13 empty] | Image Development
| Determine if standard settings for Photoshop CS6 can be deployed | [13 empty] | Image Development
| Determine standard settings for CUPC/Jabber | [13 empty] | Image Development
| Determine standard settings for Sophos Anti-virus | [13 empty] | Image Development
| Determine standard settings for Universal Type Client | [13 empty] | Image Development
| Determine standard settings for Absolute Manage Client | [13 empty] | Image Development
| Determine standard settings for i1Profiler | [13 empty] | Image Development
| Determine standard settings for VPN Client | [13 empty] | Image Development
| Determine standard settings for NEC ImageDirect | [13 empty] | Image Development
| Determine standard settings for Wacom Tablet Driver | [13 empty] | Image Development
| Determine standard settings for Bizhub 501 and C353 Print Drivers | [13 empty] | Image Development
| Determine standard settings for Xerox EFI Fiery Print Drivers | [13 empty] | Image Development
| Create spreadsheet list of applications, versions and updates to be deployed | 2013-02-25 | [6 empty] | 2013-03-08 | [5 empty] | Image Development
| Create spreadsheet list of settings packages for applications to be deployed | 2013-02-25 | [6 empty] | 2013-03-08 | [5 empty] | Image Development
| Determine settings to disable updates and administrative software functionality for all 3rd party apps | [13 empty] | Image Development
| Determine any desktop-specific settings | [13 empty] | Image Development
| Determine any laptop-specific settings | [13 empty] | Image Development
| Work with Mac Pros to design standard base image | [13 empty] | Image Development
| Work with Mac Pros to create deployment packages for applications and settings | [13 empty] | Image Development
| Centrify - Training users password set to never expire; show as expired when logging in | [13 empty] | Image Development - Issues
| Outlook 2011 -- When attempting to use Kerberos, are told "This server does not use" (Do we need to use Kerberos?) | [13 empty] | Image Development - Issues
| Shortcuts to both NY and DT Groups and userfolders added to image | [13 empty] | Image Development - Issues
| Deploy alpha configuration to all Systems users | [13 empty] | Image Testing
| Work with Mac Pros to implement necessary changes to image / deployment packages determined from Systems testing | [13 empty] | Image Testing
| Create beta configuration based on changes, update spreadsheet | [7 empty] | 2013-04-05 | [5 empty] | Image Testing
| Deploy beta configuration to 1-2 users from each department of Creative, Design and Production | [11 empty] | Lee Land, Adam Stanford are interested in testing. Beth Hunwick also tested last time and was an ideal test candidate. |  | Image Testing
| Log issues, errors and settings changes to spreadsheet created in internal testing | [13 empty] | Image Testing
| Work with Mac Pros to implement necessary changes to image / deployment packages determined from Expanded testing | [13 empty] | Image Testing
| Create release/production configuration based on changes, update spreadsheet | [7 empty] | 2013-04-19 | [5 empty] | Image Testing
| Design test process; cover both new user installs and existing user installs | [13 empty] | Image Testing
| License Purchases complete | 2013-02-11 |  | 2/11/2013 |  |  |  |  | 2013-03-08 | [5 empty] | Licensing Prerequisites
| Determine # of Mac OS X Mountain Lion Upgrades Needed | [13 empty] | Licensing Prerequisites
| Determine # of Microsoft Office 2011 licenses needed | [13 empty] | Licensing Prerequisites
| Determine # of Centrify DirectControl Licenses Needed | [11 empty] | No licenses needed |  | Licensing Prerequisites
| Determine # of Adobe CS DS/MC licenses needed | [11 empty] | 1 |  | Licensing Prerequisites
| Determine # of FileMaker Pro 11 licenses needed | [11 empty] | No licenses needed |  | Licensing Prerequisites
| Determine # of Sophos Anti-Virus licenses needed | [13 empty] | Licensing Prerequisites
| Determine # of Extensis UTS client access licenses needed | [11 empty] | None |  | Licensing Prerequisites
| Determine # of Absolute Manage clients | [13 empty] | Licensing Prerequisites
| Determine Cisco's recommended version of CUPC/Jabber for Mountain Lion | [13 empty] | Licensing Prerequisites
| Determine if we need to purchase any additional licenses for Presence/CUPC/Jabber | [13 empty] | Licensing Prerequisites
1000 | Planning | [13 empty] | Planning
Planning
| Complete Project Plan | 2013-02-11 |  | 2/11/2013 |  |  |  |  | 2013-02-15 | [5 empty] | Planning
| Upgrade AVANTI19 (required for updates, possibly required for deployment) | [13 empty] | Planning
| Schedule image development with Mac Pros, find out if start at 3/11 target completion date of the draft image by 3/22 is possible | 2013-02-18 | [6 empty] | 2013-02-28 | [5 empty] | Planning
| Determine with Mac Pros what machines will need upgrades -- Send updated list of Macs | [13 empty] | Planning
| Put together quote request for systems, accessories and licenses necessary for upgrades and send to Mac Pros (Displays, Mice, Keyboards, BookEndz, Tablets, Scratch Disks, 32 GB memory for retouchers and color specialists, 16 GB for designers, AppleCare, extra power supplies, (Mini) DisplayPort to DVI, Thunderbolt to Ethernet), also spare mac laptop and spare mac desktop | 2013-02-11 |  | 2/11/2013 |  |  |  |  | 2013-03-08 | [5 empty] | Planning
| Request quote and scope of work documentation from Mac Professionals | [13 empty] | Planning
| Create spreadsheet of machine upgrades and accessories needing to be purchased | [13 empty] | Planning
| Can AVANTI19/29 run Mountain Lion server? If not, may require upgrade. | [13 empty] | Planning
| What existing hardware that is not being used can we use to upgrade outdated Macs? | [13 empty] | Planning
| Determine FTP Client | [11 empty] | FileZilla |  | Planning
| Divide DT users into 3 groups | [13 empty] | Planning
| Schedule deployment/training for Group 1 | [11 empty] | Training should immediately follow deployment, and should cover Mac OS X Snow Leopard |  | Planning
| Schedule deployment/training for Group 2 | [11 empty] | Training should immediately follow deployment |  | Planning
| Schedule deployment/training for Group 3 | [11 empty] | Training should immediately follow deployment |  | Planning
| Schedule deployment/training for New York | [11 empty] | Training should immediately follow deployment |  | Planning
| NY's Disk Tracker application may not work on Mountain Lion, test. Inform David Laubach and Pete / Liza / Tom Chicoine. | [13 empty] | Planning
| Review Project Plan with IT Manager | [13 empty] | Planning
| Once Project Plan approved by IT Manager, speak to Mac Professionals regarding scheduling | [13 empty] | Planning
| Plan upgrade for Rick Ruffner, taking into account his iPhoto Library, Readerware, and any other software his computer has that may break upon upgrade | [13 empty] | Planning
| Once Mac Professionals hss confirmed scheduling, speak with Department heads, see if there is any issue with tentative deployment dates | [13 empty] | Planning
| Speak to Lee Land about Photoshop configuration settings for Retouchers vs Art Director -- where is this at? | [13 empty] | Planning
| Determine what we need Mac Pros to do, create SOW for this, and quote | [13 empty] | Planning
| Confirm settings are appropriate with Systems | [13 empty] | Planning
| Determine standard process for image deployment to new machines with preexisting users; document it | [13 empty] | Process Development
| Determine standard process for image deployment to existing machines with preexisting users; document it | 2013-02-25 | [6 empty] | 2013-03-22 | [5 empty] | Process Development
| Determine standard process for image deployment to machines with new users, document it | [13 empty] | Process Development
| Determine standard process for decommissioning machines, document it | [13 empty] | Process Development
| Determine standard process for purchasing machines, document it | [13 empty] | Process Development
| Determine OS / Application update process for updated configuration, document it (Mac OS X 10.8 server is critical path for our updates) | [13 empty] | Process Development
| Determine process to update images and deployment packages going forward, document it | [13 empty] | Process Development
| Create training materials for Office 2011 | [13 empty] | Training
| Create training materials for Mac OS X 10.8 | [13 empty] | Training
| Create training materials for CUPC / Jabber (if updated) | [13 empty] | Training
| Create training materials for VPN client (if updated) | [13 empty] | Training
| Design / plan training format - Location, Length of Time, Lunch, interactive / noninteractive, handouts, sign in sheet, certificate of completion | [13 empty] | Training
| Schedule use of training room (if necessary) | [13 empty] | Training
| Train Group 1 | 2013-05-27 | [6 empty] | 2013-05-31 | [5 empty] | Training
| Train Group 2 | 2013-06-10 | [6 empty] | 2013-06-14 | [5 empty] | Training
| Train Group 3 | 2013-06-24 | [6 empty] | 2013-06-28 | [5 empty] | Training
| Train NY users | 2013-07-04 | [6 empty] | 2013-07-05 | [5 empty] | Training
Special Considerations
Determine what will need to be done to upgrade Rick