## Slide 1
ynman
Team

## Slide 2: Introduction to Team: Individual Skillsets
Erik Johnson
  Language of choice: C++
  Other languages: VBScript, Bash, Windows Batch, Javascript, C#
  Strengths: Project management experience, CS research experience, detail-oriented.
Durwin Johnson
  Language of choice: C++
  Other languages: lesser degrees of c#, visual basic, and Java
  Strengths:
Alex Pope
  Language of choice: C++
  Other languages:
  Strengths: Organization
Cindy Samano
  Language of choice: C++
  Other languages:
  Strengths: Communication, methodical, goal-oriented.

## Slide 3: Introduction to Team: Individual Skillsets: Project Managers
Reggie Jirigesu
  Strengths:
Wenhao Zhang
  Strengths:

## Slide 4: Introduction to Team : Team Skillsets
Strengths:
  Experience with flat-files
  Know C++ programming language
  Communicative
  Team dynamic: personalities do not clash
  Positive attitude
  Thorough investigation of customer requirements
Weaknesses:
  Time management
  Inexperience
Notes: Weaknesses:
Time Management: Overconfidence in achieving goals and deadlines
Inexperience:

## Slide 5: Introduction to Team: Roles and Responsibilities
Team Members | Role | Responsibility
Erik Johnson | Team Lead | Coordinating development team’s tasks. Transcribing meeting minutes. Submitting Progress report to customer and Project Managers Team signoffs on artifacts.
Durwin Johnson | Developer | Producing artifacts related to the project Communicating with the Project Managers Presenting finalized copy of the project Completing tasks assigned by team lead
Alex Pope | Developer | 
Cindy Samano | Developer | 
Reggie Jirigesu | Project Manager | Review and sign off on SPMP artifacts Sign off on progress reports Provide guidance and recommendations with all aspects of project.
Wenhao Zhang | Project Manager | 
Notes: SPMP Task(s)
Erik
1.4 Performance/Behavior Constraints
2.1 Historical Data Used for Estimates
2.2.1 SPMP Completion Estimate
2.2.2.1 Lines-of-Code Estimate
2.2.2.2 Function Estimate
5.0 Staff Organization (all)
Meeting Minutes
Tool Management
Durwin
2.2.2.3 Tasks Estimate
2.2.2.4 Total Overall Project Time Estimate
2.5 Project Resource
4.1 Project Task Set
4.2 Task Network Diagram
4.3 Timeline Chart (Milestones)
Alex
1.2 Project Scope (all)
1.5 Management and Technical Constraints (all)
3.0 Risk Management (all)
2.3 Estimation Techniques Applied Results (all)
2.4 Reconciled Estimate
Cindy
Communication plan
Exception calendar
Availability sheet
1.1 Problem Statement
1.3 Major Software Functions
6.0 (all)
SPMP Reformatting
SPMP Compilation
Presentation Tasks

## Slide 6: Additional functionality
A company-wide sale on a particular item
Frequently out of stock or over stock of an item, have system order more or less, respectively, than the default upon reorder.
Coupled (related) items
Customer eligibility for refilled on other prescriptions based off refill date.
Customer coupons that provide a discount
Notes: A company: Wide sale on a particular item: when item X gets rung up a discount is applied
Frequently out of stock or over stock: If we run out of stock of an item frequently, have system order more than the default upon reorder, and if we never run out of stock by X units, have system order less than the default. This will be based on an item threshold that has been increased/decreased
Coupled items: If a customer purchases item X and item X and Y are coupled, a message asking if the customer would like to add item Y to their order is displayed so the cashier can ask
Based off the refill date of the customer's last order, check all of their prescriptions and see if any are eligible for refill, and if so, display a message to indicate to the cashier to ask the customer if they want that prescription refilled

## Slide 7: Technology We Plan to Use
Programming language: C++
Complier: Visual Studio
The program will use command line interface
Notes: The team is most familiar with C++.
Since we will be building with visual studio the program will be limited to machines that are compatible with visual studio
The program will use a command window as its input/output source due to our skill set limitations as well.

## Slide 8: Technology We Plan to Use Tools used
Communication tools:
  Slack: Main method of communication between team members.
  Google Docs and Google Calendar
Organization tools:
  Wrike Project Management: Used to assign tasks to both team members and Project Managers.
  Microsoft project: Used to create the network diagram and timeline chart.
  GitHub: Used for versioning of documents.
Time Tracking tool:
  Toggl: Used to keep track of time on tasks and meetings.
Notes: Communication tools:
  Slack: Main method of communication between team members.
  Google Docs and Google Calendar
Organization tools:
  Wrike Project Management: Used to assign tasks to both team members and Project Managers.
  Microsoft project: Used to create the network diagram and timeline chart.
  GitHub: Used for versioning of documents.
Time Tracking tool:
  Toggl: Used to keep track of time on tasks and meetings.

## Slide 9: Technology We Plan to Use Justification of Tools
Slack: Free, previous experience, intuitive, better organization than a group text, log all conversation, mobile app
Wrike: Free, previous experience, easy to assign tasks, keeps you notified, mobile app
Toggl: Free, previous experience, mobile app, reports(team functionality depends on this), time collection for team.
GitHub: Free, ubiquitous, mature, retention of historical versions of artifacts.
Microsoft Project: Most accessible way to build task network diagram.
Notes: Since these are the tools we will be using throughout the entirety of the project we felt as though we need to justify them:

## Slide 10: Estimates Part 1 Estimate
SPMP completion Estimate: 60 Hours
Notes: SPMP Completion: Based on previous experience with similar but smaller templates from past Computer Science classes, we Estimate the SPMP will take approximately 60 Hours to complete.

## Slide 11: Estimates Overall Project initial
Overall Project initial
  Lines of code: 5000 lines of code, 102 Hours
  Function Estimate: 18 functions
  Task Estimate: 46 Hours per person, 184 Hours total
  SPMP completion Estimate: 60 Hours
Total Overall Project time Estimate: 162 Hours
Notes: Initial project Estimates:
As a basis for our Estimates we drew upon on Erik’s current work experience, a lines of code per hour formula, and sampling of previous projects. Sampling previous projects allowed us to determine which projects are significant enough to be included in the lines of code per hour formula. Erik’s current work experience will give us insight into how much time and effort it will actually take to complete the project. A lines of code per hour formula was applied to major programming projects from CIS 200 and up for each team member.
  Lines of code: Based on prior experience with previous computer science projects, we Estimate this project to require 5000 lines of code. 5000 total lines divided by the team average of 49 lines of code per hour giving us102 hours
  Function Estimate: We counted the functions present in 1.3, the Major Software Functions, and used them for the function point estimation. The lowest-level functionality in 1.3 is counted and added up. Totaling 18 functions
  Task Estimate: Breaking down the project into high level tasks and estimating the time in which we believed it would take to complete each task. 46hours/person , total 184 hours
  SPMP Completion: Based on previous experience with similar but smaller templates from past Computer Science classes, we estimate the SPMP will take approximately 60 Hours to complete.

## Slide 12: Estimates Actual Part 1
  Person-Hours spent so far: 116 Hours
Notes: Estimation Selection Rationale
We determined that we had spent 116 hours thus far within the time that we began working together up until today's date (2/6/2017 – 2/24/2017). We then determined the number of days left until the final project is due – 4 days left in February, 31 days in March, due on the 28th of April = 63 days. We then divided the total number of days left by the number of days we had been working on the project: 63 / 18, to arrive at 3.5. We then multiplied this number by 117, to arrive at 409.5 hours. We added 116 to this number (the amount of time spent so far) and arrived at 525.5 hours. The closest to this number was the Task Estimate, which is still off by 126.5 hours. Therefore, we rejected the other Estimates and went with 525.5 person-hours.

## Slide 13: Estimates Part 2 Estimate
Switch to tasks estimate and tweak it based on findings and calculations based on findings from task one.
Tasks are more adjustable based on new information

## Slide 14: Estimates New Overall project Estimate

## Slide 15: SPMP What was easiest
1.2 Project scope
  Inclusions and exclusions
1.4 Performance/Behavior Constraints
1.5 Management and Technical Constraints
2.1 Historical Data for Estimates
2.5 Project Resources
4.1 Project task set
Notes: Tasks that were easy will be tasks that took the less amount of time to complete based on reports from toggl:
1.2 Project Scope: Laying out the team skillsets helped to identify exclusions such as using a flat-file system vs a database
1.4 Performance/Behavior Constraints: Thinking about reasonable expectations of functionality
1.5 Management and Technical Constraints:
Management constraints: Constraints are based on individual schedules and exceptions to team members availability.
Compared to the technical constaints
Technical constraints: Knowing the kinds of language we will be programming in and based on team skillset.
2.1 Historical Data for Estimates: Deciding what sources to use as historical data i.e Erik’s current job, programs that are from CIS 200 and up (excluding labs b/c we did not feel they were very representative of an individuals work)
2.5 Project Resources: Because we started having team meetings as earlier as possible we were able to have tools established before the SPMP was assigned. Something that was hard to establish but worked well for us.
4.1 Project task set: A communication plan was already in action by the time the SPMP was assigned making it easier to decide what the next steps of action would be.

## Slide 16: SPMP What was hardest
Document merging and formatting
1.3 Functional Decomposition
2.3 Estimation Techniques Applied and Results
2.4 Reconciled Estimate
4.2 Task network diagram: time consuming.
Risk management
SQA
Notes: Tasks that were hard will be tasks that took the less amount of time to complete based on reports from Toggl:
Document merging and formatting
There was no style template or discussed format of how the final SPMP would look. So everyone end up using different formats, fonts and bullet points making it harder and a waste of time when we had to put all the documents together.
1.3 Functional Decomposition
Defining the general functionality not the process. Thinking of it at a high enough level that did not discuss implementation details. This took some discussion to be able to grasp that concept. Also involved some emails to Steiner
2.3 Overall Project Estimate
Lines of code: Deciding on the methodology. We spent time discussing which individual projects we would include in our individual LOC Estimates. Then how we would get our teams average LOC/hour from that. We determined a way to find estimates for each method but it turned out to be harder than anticipated.
2.4 Reconciled Estimate
Deciding on which estimate (LOC, FP, Task) would be the final estimation for how long we think the project would take. Then deciding not to use any of them because we did not feel they where represented of the time we feel it would take.
4.2 Task Network Diagram
Deciding if wrike would be the best tool to display the TND. Upon further discussion and investigation of wrike it was decided we would assign task to team members through wrike but we will copy that same data into Microsoft Project in order to be able to display the TND and Timeline chart. Doing so was tedious and took a large amount of time.
3.0 Risk Mitigation
Discussion of possible risks and how to mitigate those risks took about an 1 hour to come to agreed upon decisions. There have also been recent events such as weather, when people are sick.
SQA
Because it was the last section of the SPMP, this required a lot of reviewing and cross checking across all other documents to make sure the contents within it were accurate and valid. Traceability.

## Slide 17: Communication Plan
Checking Slack once a day
Establish meeting dates: Recurring in-person meetings on Sundays
General Availability Doc
Exceptions Calendar
Notes: Checking Slack once a day:
  Requiring Team members to check Slack at least once per day to stay up to date with project discussions.
Establish meeting dates: Recurring in-person meetings on Sundays
  Slack channel “meeting_minutes” contained an overview of the discussions from in-person meetings.
General Availability Doc:
  Requiring team members to fill in their general availability during the week.
Exceptions Calendar:
  If team member had a change to their general availability and were not available on a specific say, they has to report it to this calendar.

## Slide 18: SCM Plan
Slack:
  Notify team members of changes to the repository through Slack.
  Meeting_minutes channel: Any changes discussed during in person meetings will be transcribed into meeting_minutes and posted onto Slack.
GitHub:
Source code: Will require one administrator review from either Cindy or Erik in order to commit to the master branch.
Non-source code(documents): Non-source code files will be located on the master branch and will not require review from administrator during part 1 of the SPMP.
Notes: Slack:
Notification of a change to the repository of either non-source code or source code files must be communicated to the other team members through Slack.
Meeting_minutes channel: Any changes discussed during in person meetings will be transcribed into meeting_minutes and posted onto Slack.
Source code:
Will require one administrator review in order to commit to master branch. When uploading new source code files it will be uploaded to a separate protected branch. In this separate branch team members will be able to upload changed files without having to worry about affecting the master branch. The master branch will act as the baseline for all artifacts. Protected branches by default require at least one review before committing to the master.
Non-source code:
Files that are non-source code can be uploaded directly to the master branch without review. Files that are still in progress will have an _ in the title. Those without a “_” will be assumed to be 100% complete.
As far as the non-source code part, that method has been working and we did notify each other on slack whenever there was a new file uploaded. There were problems such as the formatting, that were brought to our attention because of this, but the method it’s self is a good starting place

## Slide 19: What worked
Early start
Establishing in-person meetings
Selection of time tracking tool: Toggl
Training for tools
Team communication (excluding Project Managers)
Risk management
Setting milestones for ourselves
Notes: Early start:
Before the we chose teams, Durwin and Erik had discussed tools. We also had a small meeting the same day teams were chosen and had meetings since then.
Through these meetings we were able to minimize the time spent deciding on a meeting location and on the methods of communication before the SPMP was assigned.
Establishing in-person meetings:
Setting up required in-person meetings allowed us to discuss tools, skillsets and assign any tasks we knew we could expect on the SPMP
Selection of time tracking tool:
Helped with determining the Estimates. Using the reports generated in Toggl, we were able to see which tasks were taking up the most time and effort and individual times. We were able to assign tasks based on each persons individual time.
Training tools:
Checking out the tools and tracking task time. Since only one team member had prior experience with a majority of the tools, it was necessary that the other team members became acquainted with the tools and understood the terminology that came with each one i.e committing to master on GitHub
Team communication:
All team members were required to sign off on meeting minutes and check slack at least once per day. Whenever a team member had questions or concerns regarding the SPMP, those questions or concerns were always heard and discussed or answered by either another team member, Project Manager or Steiner
Risk Mitigation:
When our primary meeting location (the library ) was not open or closed early. Our risk mitigation plan was put into action and told us to met at our secondary meeting location, biggby. The biggby we chose was the midpoint from where all team members live so it was the obvious choice.
Setting milestones for ourselves
Motivated us to start working but we all started working on assigned task the night before our “self-set” milestone
      This last point will transition into the next slide

## Slide 20: What did not work
Documentation and Formatting Method of SPMP
Reviewing method
Wrike
Assigning tasks without checking dependences
Communication with Project Managers
Notes: Documentation and Formatting Method of SPMP
Not deciding on a format style earlier.
Reviewing method
Asking other team members to review things but not knowing which document to review first based on dependencies and priority
Wrike
We intended to use Wrike as a replacement tool for Microsoft Project because not all team member were accessible to it. The point of Wrike was to assign tasks to team members. For the first half of the project, that functionality of Wrike was not utilized because instead team members would just check meeting minutes (where assigned tasks were also mentioned because tasks were usually assigned during in-person meetings) Wrike only contained the SPMP tasks but not the little tasks in between such as sending emails, uploading meeting_minutes or progress reports.
Assigning tasks without checking dependences
Not properly checking the dependency of one task to another, put other people behind and cased a shift in work load for one person.
Communication With Project Managers
We added them onto our groups on Slack, Wrike, and GitHub. We did not add them to the general availability or exception calendar. But we asked them if they would be able to join us for our weekly Sunday meetings and they said that for the most part yes. We had drafts of the SPMP ready and we asked them to take a look at them through GitHub. They were a bit slow with the reviews and they did not give detailed feedback. At the end of Part1 we realized that the communication process was not well defined. We did not assign specific tasks to them and they did not know when or which parts of the SPMP to check first, they also were not told where to leave comments and feedback which in turn could be the reason why we felt we did not received adequate feedback.

## Slide 21: Changes for Part 2
Documentation method
Organize Repository
Review method
Communication with Project Managers
Utilize Wrike more
Notes: Documentation method
Deciding on a format for documents i.e. what type of bullet points are we going to use, layout of page.
Organize Repository
Moved all documents dealing with Phase 1 into Phase_1 folder
Created a folder "Phase 1" inside Documentation for Phase 1 items
Within Phase 1, moved individual components of the SPMP to Individual_Components and left the SPMP directly inside Phase_1
Created "Work_In_Progress" folder to be used for documentation and source you are presently working on
Created a folder for each team member by their initials inside "Work_In_Progress"
Review Method
The team has voted on using the “review” functionality on Microsoft Word to provide critiques on documents of other team members. To avoid overwriting the original, team members must make sure to save their document that contains critiques to a different name. If the document has a major dependency then the document should be reviewed first by the successor and the Project Managers.
Communication with Project Managers
Assign the Project Managers task on Wrike. Sending reminder messages about the tasks they were assigned. Add them to the general availability sheet to be aware of when they are free. Also include them in the Expectation Calendar so they can add in days they know they will not be available.
Utilize Wrike More
Assign tasks for every task that was assigned during in-person meetings. Add in due dates and approximate time due. Set tasks as completed once they are completed.

## Slide 22: Do differently in Part 1
Assign tasks quicker